ANNUAL PROGRESS REPORT

April 2018 to March 2019

KVK, Raisen (M.P.)

Under

ICAR-ATARI, Zone- IX, Jabalpur

Contents

| S. No. | Particular | Page No |
| --- | --- | --- |
|  | Instructions for Filling the Format |  |
|  | Summary of KVK Annual Report (Quantifiable Achievement) for the year 2017-18 | 3 |
| 1 | General Information | 5 |
| 2 | On Farm Testing | 9 |
| 3 | Achievements of Frontline Demonstrations | 23 |
| 4 | Documentation of the need assessment conducted by the KVK for the training programme | 33 |
| 5 | Training programmes | 34 |
| 6 | Extension Activities | 39 |
| 7 | Literature Developed/Published (with full title, author & reference) | 41 |
| 8 | Production and supply of Technological products | 41 |
| 9 | Activities of Soil and Water Testing Laboratory | 43 |
| 10 | Rainwater Harvesting | 43 |
| 11 | Utilization of Farmer Hostel facilities | 44 |
| 12 | Utilization of Staff Quarter facilities | 44 |
| 13 | Details of SAC Meeting | 44 |
| 14 | Status of Kisan Mobile Advisory | 44 |
| 15 | Status of Convergence with agricultural schemes | 45 |
| 16. | Status of Revolving Funds | 45 |
| 17. | Awards & Recognition | 45 |
| 18. | Details of KVK Agro-technological Park | 45 |
| 19. | Farm Innovators | 46 |
| 20. | KVK interaction with progressive farmers | 46 |
| 21. | Outreach of KVK | 46 |
| 22. | Technology Demonstration under Tribal Sub Plan on Pulses/ Programme on Harnessing Pulses/ Quality Protein Maize | 46 |
| 23. | KVK Ring | 46 |
| 24. | Important visitors to KVK | 47 |
| 25. | Status of KVK Website | 47 |
| 26. | Status of E-connectivity | 47 |
| 27. | Status of RTI | 47 |
| 28. | Status of Citizen Charter | 47 |
| 29. | Attended HRD activities organized by ZPD | 48 |
| 30. | Attended HRD activities organized by DES | 48 |
| 31. | Attended HRD activities by KVK Staff | 48 |
| 32 | Agri Alert report | 49 |
| 33. | Details of Technological Week Celebration | 49 |
| 34. | Interventions on Drought Mitigation | 50 |
| 35. | Satellite Village on Doubling Farmer’s Income | 52 |
| 36. | Nutri Smart Village | 54 |
| 37. | Sansad Adarsh Gram | 57 |
| 38. | Proposal of NICRA | 57 |
| 39. | Proposed works under NAIP | 58 |
| 40. | Case study / Success Story to be developed | 58 |
| 41. | Action Photographs | 60 |

REPORTING PERIOD – April 2018 to March 2019

Summary of KVK Annual Report (Quantifiable Achievement)  for  the  year  2018-19

| S.N. | Quantifiable Achievement | Number | Beneficiaries (nos.) |  |
| --- | --- | --- | --- | --- |
| 1 | On Farm Testing |  |  |  |
|  | Proposed OFT | 22 | 105 |  |
|  | On Going OFT | - | - |  |
|  | Technologies assessed (Completed OFT) | 22 | 105 |  |
|  | Technologies refined | - | - |  |
|  | On farm trials conducted | 22 | 105 |  |
| 2 | Frontline demonstrations |  |  |  |
|  | Proposed Frontline demonstrations | 18 | 110 |  |
|  | On Going Frontline demonstrations | - | - |  |
|  | FLDs conducted on crops | 11 | 60 |  |
|  | Area under crops (ha.) | 19.5 | 60 |  |
|  | FLD on farm implement and tools | - | - |  |
|  | FLD on livestock/ AH enterprises (Dairy/ Sheep and Goat/Poultry/ Duckery/ Piggery etc.) | 3 | 30 |  |
|  | FLD on Fisheries - Finger lings | - | - |  |
|  | FLD on other enterprises (Bee keeping, lac, mushroom, sericulture, value addition, vermi compost, etc.) | - | - |  |
|  | FLD on Women in Agriculture - (Nutritional garden, Income generation, Value addition, Drudgery reduction, etc.) | 4 | 20 |  |
| 3 | Training programmes | No. of Course | Duration (days) | Participants |
|  | Farmers | 67 | 1 | 1387 |
|  | Farm women | 10 | 1 | 236 |
|  | Rural youth | 3 | 5 | 70 |
|  | Extension personnel/ In service | 2 | 1 | 47 |
|  | Vocational trainings | - | - | - |
|  | Sponsored Training | - | - | - |
|  | Total | 82 | - | 1740 |
|  |  | No. of programmes | Participants |  |
| 4 | Extension Programmes | 159 | 3368 + Mass |  |
| 5 | Production of technology inputs etc | Qty | Beneficiaries (nos.) |  |
|  | Seed (qt.) | 439.4 | - |  |
|  | Planting material produced (nos.) | 10100 | - |  |
| 6 | Livestock | Qty | Beneficiaries (nos.) |  |
|  | Livestock strains ( Nos) | - | - |  |
|  | Milk Yield - Cow, Buffelo etc. (in liter) | - | - |  |
|  | Fish (Kg.) | - | - |  |
|  | Fingerlings (nos.) | - | - |  |
|  | Poultry-Eggs (nos.) | - | - |  |
|  | Ducks (nos.) | - | - |  |
|  | Chicks etc. (nos.) | - | - |  |
| 7 | Bio Products | Qty | Beneficiaries (nos.) |  |
|  | Bio Agents -Earth worm (Kg.) | - | - |  |
|  | Trichoderma (kg.) | - | - |  |
|  | Bio Fertilizers- Vermi compost, Rhizobium, PSB , BGA , Mycorriza , Azotobacter , Azospirillum etc. (Kg.) | - | - |  |
|  | Bio Pesticide-Panchgavya, Neem Extract , Neem oil etc.(lit.) | - | - |  |
| 8 | Any other significant achievement in the Zone | Nos. | Participants/ beneficiaries |  |
|  | Award (Best KVK award and scientist and farmer’s award) | 3 | 3 |  |
|  | Publications ( Res. Paper/ pop. Art./Bulletin,etc.) | 18 | 3000+ Mass |  |
|  | KVK News letter | 4 | 4000 |  |
|  | SAC Meetings conducted | 1 | 20 |  |
|  | Soil sample tested | 525 | 525 |  |
|  | Water sample tested | - | - |  |
|  | RWH System (Special training and field visit on RWH structure and MIS in KVKs) | - | - |  |
|  | KVK-KMA (Message and beneficiaries) | 43 | 48500 |  |
|  | Convergence programmes | 2 | 40 |  |
|  | Sponsored programmes | - | - |  |
|  | KVK Progressive Farmers interaction | - | - |  |
|  | No. of Technology Week Celebrations | - | - |  |
|  | Attended HRD activities organized by ZPD | 4 | 4 |  |
|  | Attended HRD activities organized by DES | 2 | 2 |  |
|  | Attended HRD activities by KVK Staff(Refresher /Short course, Training programme etc. ) | - | - |  |
| 9 | Current status of Revolving Funds ( Amt. in Rs.) | - |  |  |
| 10 |  | No. of blocks | No. of villages |  |
|  | Outreach of KVK in the District | 7 | 104 |  |
| 11 |  | ICAR | SAU | Others |
|  | No. of important visitors to KVK (nos.) | 1 | 1 | 6 |
| 12 |  | Working (Yes/No) | No. of Update |  |
|  | Status of KVK Website | Yes | 155 |  |
| 13 |  | Application received | Application disposed |  |
|  | Status of RTI (nos.) | - | - |  |
| 14 |  | Query received | Query dissolved |  |
|  | Citizen Charter (nos.) | - | - |  |
| 15 |  | Working (Yes/No) | No. of programme viewed |  |
|  | E-connectivity | No | - |  |
| 16 |  | Filled | Vacant |  |
|  | Staff Position | 14 | 2 |  |
| 17 | Workshop/ Seminar/ Conference attended by staff of KVK ( nos) |  |  |  |
| 18 | Publication received from ICAR /other organization (nos.) | 4 |  |  |
| 19 |  | Particulars | Organization |  |
|  | Agri alerts (epidemic, high serious nature problem, Cyclone etc. reported first time to ZPD, SAU, Agri. Deptt. and ICAR) | - | - |  |
| 20 | Activities performed in Satellite Village on DFI | Nos. of Activities | Participants/ beneficiaries |  |
|  |  | 10 | 166 |  |
| 21 | Activities performed in Nutri Smart Village | Nos. of Activities | Participants/ beneficiaries |  |
|  |  | 20 | 434 |  |
| 22 | Activities performed in Sansad Adarsh Gram | Nos. of Activities | Participants/ beneficiaries |  |
|  |  | - | - |  |

GENERAL INFORMATION

1.1. Staff Position (as on date)

Summary of Staff position in  KVKs  on  March, 2019

| Name of KVK | Sanctioned Posts | PC (1) |  | SMS (6) |  | PA (3) |  | Admn. (6) |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Sanc. | Filled | Sanc. | Filled | Sanc. | Filled | Sanc. | Filled | Sanc. | Filled |
| Raisen | 16 | 1 | 1 | 6 | 4 | 3 | 3 | 6 | 6 | 16 | 14 |

| Name of KVK | Sanction post | Name of the incumbent | Discipline | Higist degree | Subject of specilization | Pay scale | Present pay | Date of joiing | Per./Temp. | Category |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Raisen | Programme Coordinator | Dr. Swapnil Dubey | Agronomy | M.Sc (Ag), Ph.D. | Agronomy | 37400-67000 G.P. 9000 | 52240 | 1st July, 2014 | Permanent | GEN |
| Raisen | Subject Matter Specialist2 | Mr. Ranjeet Singh Raghav | Soil Science | M.Sc. (Ag.) | Soil Science | 15600-39100 G.P. 5400 | 23640 | 1st July, 2014 | Permanent | GEN |
| Raisen | Subject Matter Specialist3 | Ms. Lakshmi Chakravarti | Home Science | M.H.Sc. (Food & Nutrition), M.Phil. | Home Science | 15600-39100 G.P. 5400 | 23640 | 1st July, 2014 | Permanent | OBC |
| Raisen | Subject Matter Specialist4 | Mr. Pradip Kumar Dwivedi | Plant Protection | M.Sc. (Ag.) (Entomology), MBA. | Plant Protection | 15600-39100 G.P. 5400 | 22950 | 1st April, 2015 | Permanent | GEN |
| Raisen | Subject Matter Specialist5 | Mukul Kumar | Horticulture | M.Sc. (Ag.) (Horticulture) | Horticulture | 15600-39100 G.P. 5400 | 22280 | 3rd Feb, 2016 | Permanent | GEN |
| Raisen | Subject Matter Specialist1 | Vacant | Agriculture Extension | - | - | - | - | - | - | - |
| Raisen | Subject Matter Specialist6 | Vacant | Fisheries | - | - | - | - | - | - | - |
| Raisen | Programme Assistant | Dr. Anshuman Gupta | Veterinary Science | B.V.Sc & AH, MSW & PGDRD | Animal Science | 9300-34800 G.P. 4200 | 21740 | 25th March, 2004 | Permanent | GEN |
| Raisen | Farm Manager | Mr. Sunil Kethwas | Farm Manager | B.Sc (Ag.) | - | 9300-34800 G.P. 4200 | 18180 | 10th Oct, 2007 | Permanent | SC |
| Raisen | Computer Programmer | Mr Pankaj Bhargava | Computer Science | MCA | Computer Science | 9300-34800 G.P. 4200 | 21740 | 8th April, 2004 | Permanent | GEN |
| Raisen | Accountant / superintendent | Mr. Rajkumar Makode | Accounts | M.Com. | - | 9300-34800 G.P. 4200 | 16630 | 1st July, 2011 | Permanent | OBC |
| Raisen | Stenographer | Mrs. Aruna Somkunwar | Stenographer | M.A & PGDRD | Stenography | 5200-20200 G.P. 2400 | 14770 | 22nd March, 2004 | Permanent | SC |
| Raisen | Driver | Mr. Ubed Khan | Jeep Driver | 10th | - | 5200-20200 G.P. 2000 | 11900 | 5th February, 2005 | Permanent | GEN |
| Raisen | Driver | Mr. Vijay Kumar Sahu | Tractor Driver | 10th | - | 5200-20200 G.P. 2000 | 7650 | 1st Apr, 2016 | Permanent | OBC |
| Raisen | Supporting staff | Mr. Sanjay Chaudhary | Supporting Staff | B.Com. | - | 5200-20200 G.P. 1800 | 9730 | 7th April, 2006 | Permanent | SC |
| Raisen | Supporting staff | Mr. Devendra Dange | Supporting Staff | 12th | - | 5200-20200 G.P. 1800 | 7000 | 1st Nov., 2018 | Temporary | SC |

1.2. DISTRICT PROFILE (detail of geographical area, cultivation, Land, resources, opportunities, irrigation, populations etc.)–

| KVK Name | Agro-climatic zone | No . of Blocks | No. of Panchayats | Population | Literacy | SC and ST Population | No. of farmers | Average land holding |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Raisen | Vindhyan Plateau | 07 | 502 | 13,31,699 | 74.3% | 3,61,373 | 1,08,499 | 4.064 |

1.3. DETAILS OF ADOPTED VILLAGE during the reporting period (Approved by competent Authority in meetings/workshops)

| KVK Name | Village Name | Year of adoption | Block Name | Distance from KVK | Population | Number of farmers (having land in the village) |
| --- | --- | --- | --- | --- | --- | --- |
| Raisen | Bhanpur Garhi | 2014 | Gairatganj | 40 | 850 | 90 |
| Raisen | Hinotiya Khas | 2014 | Gairatganj | 37 | 800 | 125 |

1.4. THRUST AREAS identified by KVK (Approved by competent Authority in meetings/workshop)

| KVK Name | THRUST AREA |
| --- | --- |
| Raisen | Integrated Crop Management Practices |
| Raisen | Use of high yielding variety |
| Raisen | Crop Diversification |
| Raisen | Application of Balance dose of fertilizers |
| Raisen | Integrated Pest Management Techniques |
| Raisen | Horticulture & Vegetable Crops |
| Raisen | Use of high yielding variety |
| Raisen | Commercial fruit & vegetables cultivation |
| Raisen | Nursery raising |
| Raisen | Rejuvenation of old orchards |
| Raisen | Livestock Management |
| Raisen | Dairy Management |
| Raisen | Goatry Management |
| Raisen | Feed Management |
| Raisen | Disease Management |

1.4. PROBLEM IDENTIFIED by KVK (Approved by competent Authority in meetings/workshop)

| KVK Name | Problem identified | Methods of problem identification | Location Name of Village & Block |
| --- | --- | --- | --- |
| Raisen | Low yield of Soybean due use of old variety (JS 93-05) | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Poor insect -pests management due to injudicious use of chemical insecticides | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low yield of paddy due to false smut disease of paddy | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Sheath blight & stem borer is one of the major problem in the district causing serious yield losses | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low yield of Ginger due use of traditional variety. | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low yield of rice due to physiological disorder khaira disease. | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low yield due to sowing of old varieties | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low yield of chick pea due to high incidence of wilt disease and infestation of gram pod borer | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Poor production and low keeping quality | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low yield of Tomato due to Leaf Curl Virus and Early blight | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Poor nitrogenous fertilizer use efficiency | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Deteriorating soil organic carbon content | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low yield due to inadequate dose of fertilizers | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | If wheat sowing is delayed yield of wheat reduce | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low milk production in dairy animals. | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low milk yield due to lack of essential mineral, energy protien & salt rich diet. | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low milk yield due to lack of protein rich fodder in dairy animal | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Poor knowledge about SHC recommendation | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | 30% losses in pulses during storage. | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low efficiency and improper seed treatment | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | Low income of farm women due to improper management of bio-waste | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |
| Raisen | High mortality of seed during seedling preparation & low income of farm women during vegetable production | PRA/Group Discussion | Bhanpur Garhi & Hinotiya Khas/ Gairatganj Block |

2. On Farm Testing (OFT)

Thematic Areas for OFT/FLD

| Thematic Areas for OFT/FLD | Parameters Name and unit |
| --- | --- |
| OFT/FLD on Crops |  |
| Agro Forestry | Yield q/ha |
| Crop Diversification | insect population/plant |
| Integrated Crop Management | No of pods/plant |
| Integrated Farming system | Disease incidence % |
| Integrated Disease Management | No of effective tillers/hill |
| Integrated Nutrient Management | Rhizome wt/Plant(g) |
| Integrated Weed Management | No of weeds/m2 |
| Varietal Evaluation | Fruit wt(g) |
| Integrated Pest Management | No of Fruits/plant |
| Integrated Plant Nutrient Management | Fruit Length(cm) |
| Feed and Fodder Production | No of nodules/plant |
| Resource conservation Technology | % Insectitation |
| Soil Fertility Management | No of Cobs/plant |
|  | No of Larvae/m2 |
|  | No of Panicles/m2 |
|  | No of Tillers/hills |
|  | No of Bulb weight(g) |
|  | No of Grains/panical |
|  | No. of tubers/plant |
|  | Weight of Curd/head (g/plant) |
|  | No. of Siliquae or Capsule /plant |
|  | Seedling Germination (%) |
| OFT/FLD on Agriculture Engineering |  |
| Farm Mechanization | Yield (q/ha) |
| Resource Conservation Technology | Field Capacity (ha/hr) |
| Post-Harvest Management | Cleaning efficiency % |
| Storage loss minimization Technology | Cleaning Capacity q/hr |
| Small Farm Implements | weed population per m2 |
|  | tillers/plant |
|  | water inefficiency |
|  | irrigation efficiency |
| OFT/FLD on Animal Science |  |
| Animal Feed / Fodder Management | Milk yield (Lit/day/animal) |
| Animal Disease Management | change in body weight(kg) |
| Animal Nutrition Management | Egg Production/bird/year |
| Livestock production & management | % decrease in Worm |
| Animal breed evaluation | Parasite control (%) |
| Poultry Production and management | Body weight at 12 month (kg/goat) |
|  | Parasite occurrence (%) |
|  | Live weight (kg/bird) at 12th Month |
|  | Growth Rate (90 days) |
|  | Yield q/ha (Fodder) |
|  | Mortality % |
|  | Feed intake |
|  | % Disease infestation |
| OFT/FLD on Fisheries |  |
| Fingerling Production in Seasonal Ponds | Yield (q/ha) |
| Composite Fish Farming | Yield (q/ha), ABW (kg) |
| Fish Nutrition | Survival Rate (%) |
| Fish-cum-Duck Farming | Disease incidence (%) |
| Fish Production & Management |  |
| Fish Breeding |  |
| Fish Seed Production |  |
| Spawn to fry production |  |
| Integrated Farming System |  |

2.1	Details of OFT on Crop

| KVK name | Year/ Season | Problem diagnose | Title of OFT | Category | Name of Technology/Variety used |  |  | Thematic Area | Crop Category | Name of Crop | Farming Situations | Target | No. of trials | Results (with parameter) |  |  | Net Returns (Rs./ha) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | T1 | T2 | T3 |  |  |  |  |  |  | FP (T1) | RP (T2) | T3 | FP (T1) | RP (T2) | T3 |
| Raisen | Kharif-2018 | Low yield of Soybean due use of old variety (JS 93-05) | Assessment of ridge and furrow technology in improved variety of Soybean JS 20-29, JS 20-69. (under Soybean –Wheat cropping center) T1: JS 93-05. T2: JS 20-29 T3: JS 20-69. | Assess. | JS 93-05 | JS 20-29 | JS 20-69. | CMP | Oilseed | Soybean | Rainfed | 05 | 05 | 9.15 | 11.4 | 13.2 | 10375 | 14000 | 17500 |
| Raisen | Kharif-2018 | Poor insect -pests management due to injudicious use of chemical insecticides | Assessment of IPM modules in Soybean. T1: No use of IPM. T2: Pheromone traps 10/ha each for Spodoptera and Helicoverpa +Seed treatment Trichoderma viride @ 10 g/kg seed + Thiamethoxam 30FS 10 ml/kg seed +Bird perches @ 50/ha + need based spray of Chlorantraniliprole 18.5 SC @ 100 ml/ha | Assess. | No use of IPM. | Pheromone traps + ST + Bird Percher Insecticide | - | IPM | Oilseed | Soybean | Rainfed | 05 | 05 | 8.9 | 11.65 | - | 9950 | 16075 | - |
| Raisen | Kharif-2018 | Low yield of paddy due to false smut disease of paddy | Assessment of Copper oxychloride and Carbendazim for the management of false smut of paddy. T1: No seed treatment and injudicious use of pesticides. T2: Seed treatment with Carbendazim @ 2 g/ kg seed prior sowing. T3: T2+ foliar spray of Copper oxychloride @ 3 g/ liter of water at the time of tillering and pre flowering stage. | Assess. | No ST | ST with carbendazim | T2+ with foliar spray of Copper oxychloride | IDM | Cereals | Paddy | Irrigated | 05 | 05 | 35.5 | 37.95 | 39.65 | 62850 | 68715 | 72855 |
| Raisen | Kharif-2018 | Sheath blight & stem borer is one of the major problem in the district causing serious yield losses | Assessment of Fungicide & Insecticide against Sheath Blight & insect pests of Rice. T1: Seed treatment by thiram. T2: Seed treatment by Carbendazim + Foliar spray of (Flubendiamide 3.5% + Hexaconazole 5% WDG) Ready mixed formulation 400g/acre at active tillering & Panicle initiation stage. T3: Seed treatment by Carbendazim + Foliar spray of Propiconazole 1ml/l followed by Cartap Hydrochoride 50% SP 1.5gm/l at active tillering & Panicle initiation stage. | Assess. | ST by thiram | ST by Carbendazim + Foliar spray of (Flubendiamide + Hexaconazole | ST by Carbendazim + Foliar spray of Propiconazole + Cartap Hydrochoride | PLP | Cereals | Paddy | Rainfed | 05 | 05 | 36.4 | 38.72 | 40.15 | 65280 | 70344 | 73805 |
| Raisen | Kharif-2018 | Low yield of Ginger due use of traditional variety. | Assessment of Improved variety of Ginger (Suprabha). T1: Use of old variety. T2: Improved variety Suprabha. | Assess. | Use of old variety | Improved variety Suprabha. | - | HOV | Vegetables | Ginger | Irrigated | 05 | 05 | 102.75 | 158.42 | - | 93500 | 181840 | - |
| Raisen | Kharif-2018 | Low yield of rice due to physiological disorder khaira disease. | Assessment of micronutrients Zinc in transplanted rice (Rice-wheat cropping system). T1: No use of micronutrient. T2: Application of micronutrient Zinc – 25 kg/ha. | Assess. | No use of micronutrient | Application of micronutrient Zinc – 25 kg/ha. | - | INM | Cereals | Paddy | Irrigated | 05 | 05 | 47.1 | 50.5 | - | 69585 | 76109 | - |
| Raisen | Rabi-2018-19 | Low yield due to sowing of old varieties | Assessment of improved wheat varieties Pusa Anmol, Pusa Tejas under Irrigated condition. T1: GW-322. T2: Pusa Anmol T3: Pusa Tejas | Assess. | GW-322 | Pusa Anmol | Pusa Tejas | CMP | Cereals | Wheat | Irrigated | 05 | 05 | 39.7 | 44.5 | 47.4 | 48900 | 57500 | 63300 |
| Raisen | Rabi-2018-19 | Low yield of chick pea due to high incidence of wilt disease and infestation of gram pod borer | Assessment of IPM in chick pea for the management of wilt disease and gram pod borer T1: No seed treatment & IPM. T2: Seed treatment with carboxin + thiram @ 2 g/kg seed followed by biofertilizers (Rhizobium + PSB cultures) @ 5 g/kg seed. T3: T2 + use of pheromone trap @ 10/ha and foliar spray of Profenophos @ 2 ml/liter of water. | Assess. | No ST | ST by carboxin + thiram @ 2 g/kg seed followed by biofertilizers (Rhizobium + PSB cultures) | T2 + use of pheromone trap @ 10/ha and foliar spray of Profenophos | PLP | Pulses | Gram | Irrigated | 05 | 05 | 12.75 | 14.25 | 15.90 | 32500 | 37500 | 43600 |
| Raisen | Rabi-2018-19 | Poor production and low keeping quality | Assessment of HYV onion for good keeping quality. T1: Agrifound Light Red (ALR). T2: Bhima Red T3: Bhima Shakti | Assess. | Agrifound Light Red (ALR). | Bhima Red | Bhima Shakti | HOV | Vegetables | Onion | Irrigated | 05 | 05 | 258.51 | 356.12 | 410.00 | 66675 | 101061 | 128001 |
| Raisen | Rabi-2018-19 | Low yield of Tomato due to Leaf Curl Virus and Early blight | Assessment of HYV variety Arka Rakshak of Tomato. T1: Local Variety T2: Arka Samrat T3: Arka Rakshak | Assess. | Local Variety | Arka Samrat | Arka Rakshak | HOV | Vegetables | Tomato | Irrigated | 05 | 05 | 190.65 | 345.50 | 450.75 | 20325 | 62750 | 115375 |
| Raisen | Rabi-2018-19 | Poor nitrogenous fertilizer use efficiency | Assessment of Neem coated urea for enhancing -N use efficiency in wheat. T1: Nitrogen at the time of 20 DAS. T2: Neem Coated Urea @ 120 kg/ha (50% of N at the time of sowing +25 % at 20 DAS +25% at 40 DAS). | Assess. | Nitrogen at the time of 20 DAS. | Neem Coated Urea @ 120 kg/ha (50% of N at the time of sowing +25 % at 20 DAS +25% at 40 DAS). | - | INM | Cereals | Wheat | Irrigated | 05 | 05 | 45.3 | 48.6 | - | 72100 | 78700 | - |
| Raisen | Rabi-2018-19 | Deteriorating soil organic carbon content | Assessment of Bio-waste decomposer for quality organic product to enhance soil health. T1: Dumping the farm waste and residue in pits exposed to extreme weather conditions. T2: 250 gm consortium mix 2 Kg of jiggery in 200 liter of water in a container. | Assess. | Dumping the farm waste and residue in pits exposed to extreme weather conditions. | 250 gm consortium mix 2 Kg of jiggery in 200 liter of water in a container. | - | NRM | - | - | Irrigated | 05 | 05 | - | Result awaited | - | - | - | - |
| Raisen | Rabi-2018-19 | Low yield due to inadequate dose of fertilizers | Assessment of nutrient management on STV basis in wheat under irrigated condition. T1: Use 75 kg DAP (18:46:0) , 250 kg urea /ha. T2: Use of NPK @ 140:70:35 kg/ha + 5 kg Zn through ZnSO4 T3: Use of Biofertilizers + 75 % NPK @ 105:52.5:26.3kg/ha + 3.75 kg Zn through ZnSO4. | Assess. | Use 75 kg DAP (18:46:0) , 250 kg urea /ha. | Use of NPK Zn | Use of Biofertilizers + 75 % NPK | INM | Cereals | Wheat | Irrigated | 05 | 05 | 45.5 | 50.3 | 46.8 | 72500 | 78800 | 76750 |

Recommendations of OFTs

| Recommendations |  |  |
| --- | --- | --- |
| Title of OFT | For Farmers | For Deptt. Personnel |
| - | - |  |

  - Economic Performance

| OFT Title | Parameters |  |  |  | Average Cost of cultivation (Rs/ha) |  |  | Average Gross Return (Rs/ha) |  |  | Average Net Return (Rs/ha) |  |  | Benefit-Cost Ratio (Gross Return / Gross Cost) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name and unit of Parameter | FP (T1) | RP (T2) | (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) | FP (T1) | RP(T2) | Refined Practice, if any (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) |
| Assessment of ridge and furrow technology in improved variety of Soybean JS 20-29, JS 20-69. (under Soybean –Wheat cropping center) | Pods/plant (No.) | 18.5 | 22.5 | 27.5 | 12500 | 14500 | 15500 | 22875 | 28500 | 33000 | 10375 | 14000 | 17500 | 1.83 | 1.96 | 2.12 |
| Assessment of IPM modules in Soybean. | No. of Larve/m2 | 3.12 | 0.50 | - | 12300 | 13300 | - | 22250 | 29375 | - | 9950 | 16075 | - | 1.80 | 2.20 | - |
| Assessment of Copper oxychloride and Carbendazim for the management of false smut of paddy. | Disease incidence % | 4.75 | 1.00 | 0.50 | 33000 | 33750 | 34200 | 95850 | 102465 | 107055 | 62850 | 68715 | 72855 | 2.90 | 3.03 | 3.13 |
| Assessment of Fungicide & Insecticide against Sheath Blight & insect pests of Rice. | Disease incidence % | 34.0 | 7.0 | 3.0 | 33000 | 34200 | 34600 | 98280 | 104544 | 108405 | 65280 | 70344 | 73805 | 2.97 | 3.05 | 3.13 |
| Assessment of Improved variety of Ginger (Suprabha). | Rhizome weight/plant (gm) | 172.75 | 305.14 | - | 112000 | 135000 | - | 205500 | 316840 | - | 93500 | 181840 | - | 1.83 | 2.34 | - |
| Assessment of micronutrients Zinc in transplanted rice (Rice-wheat cropping system). | Tillers/plant | 18 | 24 | - | 46165 | 50181 | - | 117750 | 126250 | - | 69585 | 76109 | - | 2.44 | 2.52 | - |
| Assessment of improved wheat varieties Pusa Anmol, Pusa Tejas under Irrigated condition. | Tillers/plant (No.) | 9.5 | 11.5 | 13.5 | 30500 | 31500 | 31500 | 79400 | 89000 | 94800 | 48900 | 57500 | 63300 | 2.60 | 2.82 | 3.00 |
| Assessment of IPM in chick pea for the management of wilt disease and gram pod borer | Disease incidence % | 30.0 | 7.0 | 2.0 | 18500 | 19500 | 20000 | 51000 | 57000 | 63600 | 32500 | 37500 | 43600 | 2.75 | 2.92 | 3.18 |
| Assessment of HYV onion for good keeping quality. | Bulb weight (gm) | 150 | 186.13 | 196.3 | 62580 | 76999 | 76999 | 129255 | 178060 | 205000 | 66675 | 101061 | 128001 | 2.06 | 2.31 | 2.66 |
| Assessment of HYV variety Arka Rakshak of Tomato. | Fruit weight (gm) | 80.84 | 93.40 | 95.56 | 75000 | 110000 | 110000 | 95325 | 172750 | 225375 | 20325 | 62750 | 115375 | 1.27 | 1.57 | 2.04 |
| Assessment of urea for enhancing -N use efficiency in wheat. | Test weight (gm/1000 seed) | 37.6 | 37.9 | - | 18500 | 18500 | - | 90600 | 97200 | - | 72100 | 78700 | - | 4.89 | 5.25 | - |
| Assessment of Bio-waste decomposer for quality organic product to enhance soil health. | Duration (days) | 110 | 65 | - | - | - | - | - | - | - | - | - | - | - | - | - |
| Assessment of nutrient management on STV basis in wheat under irrigated condition. | Test weight (gm/1000 seed) | 39.7 | 40.3 | - | 18500 | 21800 | 16850 | 91000 | 100600 | 93600 | 72500 | 78800 | 76750 | 3.92 | 3.61 | 4.55 |

2.3	Details of OFT on Agriculture Engineering

| KVK name | Year/Season | Problem diagnose | Title of OFT | Category of technology | Name of Technology used |  |  | Thematic Area | Crop/Enterprise Category | Crop/ enterprise | Farming Situations | Target | No. of trials | Results (with parameter) |  |  | Net Returns (Rs./ha) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | T1 | T2 | T3 |  |  |  |  |  |  | FP (T1) | RP (T2) | T3 | FP (T1) | RP (T2) | T3 |
| Raisen | Rabi-2018-19 | If wheat sowing is delayed yield of wheat reduce | Assessment of Zero till seed cum ferti. Drill for sowing wheat after paddy harvesting. | Assess. | Sowing by seed drill. | Direct sowing of wheat after paddy harvesting. | - | AEG | Cereals | Wheat | Irrigated | 05 | 05 | 38.28 | 43.75 | - | 46060 | 60000 | - |

Recommendations of OFTs

| Recommendations |  |  |
| --- | --- | --- |
| Title of OFT | For Farmers | For Deptt. Personnel |
| - | - |  |

2.4 Economic Performance

| OFT Title | Parameters |  |  |  | Average Cost of cultivation (Rs/ha) |  |  | Average Gross Return (Rs/ha) |  |  | Average Net Return (Rs/ha) |  |  | Benefit-Cost Ratio (Gross Return / Gross Cost) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name and unit of Parameter | FP (T1) | RP (T2) | (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) | FP (T1) | RP(T2) | Refined Practice, if any (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) |
| Assessment of Zero till seed cum ferti. Drill for sowing wheat after paddy harvesting. | Yield (q/ha) | 38.28 | 43.75 | - | 30500 | 27500 | - | 76560 | 87500 | - | 46060 | 60000 | - | 2.51 | 3.18 | - |

2.5	Details of OFT on Animal Science

| KVK name | Year/season | Problem diagnose | Title of OFT | Category of technology | Name of Technology used |  |  | Thematic Area | Category of Enterprise | Name of Enterprise | Target | No. of trials | Results (with parameter) |  |  | Net Returns (Rs./ha) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | T1 | T2 | T3 |  |  |  |  |  | FP (T1) | RP (T2) | T3 | FP (T1) | RP (T2) | T3 |
| Raisen | Kharif-2018 | Low milk production in dairy animals. | Assessment of cultivation and feeding of Maize fodder (ATM) for milk production in dairy animals. T1: No green fodder cultivation for feeding dairy animals. T2: Cultivation of maize green fodder & feeding @ 30 kg/animal/day. | Assess. | No green fodder | Green fodder Maize @ 30 Kg/animal /day | - | AS | Feed management | ATM | 05 | 05 | 8 | 9.8 | - | 184 | 280 | - |  |
| Raisen | Rabi-2018-19 | Low milk yield due to lack of essential mineral, energy protien & salt rich diet. | Assessment of urea molasses mineral block (UMMB) for milk production in dairy animals. T1: No use of UMMB in dairy animals. T2: Use of UMMB @ 25 kg/10 day. | Assess. | No use of Urea or urea treated fodder | Use of Urea molases Milk Block as Lick | - | AS | Nutrition management | UMMB | 05 | 05 | 9 | 10.3 | - | 193 | 250 | - |  |
| Raisen | Rabi-2018-19 | Low milk yield due to lack of protein rich fodder in dairy animal | Assessment of Azolla and Fodder production by hydroponics for feeding to dairy animals. T1: No use of Azola. T2: Azolla 1.5 kg with green fodder per day per animal. T3: T2 + Dewormer- Alvomar. | Assess. | No use of Azolla | Use of Azolla @1.5 Kg/day with normal feeding | - | AS | Feed management | Azola | 05 | 05 | 7 | 8.4 | - | 182 | 245 | - |  |

Recommendations of OFTs

| Recommendations |  |  |
| --- | --- | --- |
| Title of OFT | For Farmers | For Deptt. Personnel |
| - | - |  |

2.6 Economic Performance

| OFT Title | Parameters |  |  |  | Average Cost of cultivation (Rs/ha) |  |  | Average Gross Return (Rs/ha) |  |  | Average Net Return (Rs/ha) |  |  | Benefit-Cost Ratio (Gross Return / Gross Cost) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name and unit of Parameter | FP (T1) | RP (T2) | (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) | FP (T1) | RP(T2) | Refined Practice, if any (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) |
| Assessment of cultivation and feeding of Maize fodder (ATM) for milk production in dairy animals. | Milk in lts/day | 8 | 9.8 | - | 200 | 210 | - | 384 | 490 | - | 184 | 280 | - | 1.92 | 2.33 | - |
| Assessment of urea molasses mineral block (UMMB) for milk production in dairy animals. | Milk in lts/day | 9 | 10.3 | - | 257 | 265 | - | 450 | 515 | - | 193 | 250 | - | 1.75 | 1.94 | - |
| Assessment of Azolla and Fodder production by hydroponics for feeding to dairy animals. | Milk in lts/day | 7 | 8.4 | - | 168 | 175 | - | 350 | 420 | - | 182 | 245 | - | 2 | 2.4 | - |

2.7	Details of OFT on Fisheries

| KVK Name | Year/ Season | Problem diagnose | Title of OFT | Category of technology (Assessment/ Refinement) | Name of Technology used |  |  | Thematic Area | Category of Enterprise | Name of Enterprise | Target | No. of trials | Results (with parameter) |  |  | Net Returns (Rs./ha) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | T1 | T2 | T3 |  |  |  |  |  | FP (T1) | RP (T2) | T3 | FP (T1) | RP (T2) | T3 |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |

Recommendations of OFTs

| Recommendations |  |  |
| --- | --- | --- |
| Title of OFT | For Farmers | For Deptt. Personnel |
| - | - |  |

2.8 Economic Performance

| OFT Title | Parameters |  |  |  | Average Cost of cultivation (Rs/ha) |  |  | Average Gross Return (Rs/ha) |  |  | Average Net Return (Rs/ha) |  |  | Benefit-Cost Ratio (Gross Return / Gross Cost) |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name and unit of Parameter | FP (T1) | RP (T2) | (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) | FP (T1) | RP(T2) | Refined Practice, if any (T3) | FP (T1) | RP (T2) | Refined Practice, if any (T3) |
| - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |

2.9	Details of OFT on Agriculture Extension

| S.No | KVK Name | Season & Year | Problem identified | Title of OFT | Thematic Area | Name of Technology assessed | Source of Technology (Year) | Farmers Practice (T1) | Assessed Rec. Practice (T2) | Refined practice, if Any (T3) | Variety | No. of Village | No. of Trials (Replication) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Raisen | Rabi 2018-19 | Poor knowledge about SHC recommendation | Assessment of knowledge & adoption of soil health card based fertilizer application. T1: Farmers are not using fertilizers as per SHC Recommendation. T2: To find out the awareness, knowledge and adoption of farmers toward soil health card practices. | CBD | - | - | - | - | - | - | - | - |

Recommendations of OFTs

| Recommendations |  |  |
| --- | --- | --- |
| Title of OFT | For Farmers | For Deptt. Personnel |
| - | - |  |

2.10 Performance of OFT

| KVK Name | Name of parameter |  |  | Data on the parameter |  |  | Result of assessment |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 1 | 2 | 3 |  |
| Raisen | - | - | - | - | - | - | - |

2.11 Information about Home Science OFT: ( For All Thematic Area)

| KVK Name | Year | Season | Problem diagnose | Title of OFT | Category of technology (Assessment/ Refinement) | Thematic Area | Details of Technology Selected for Assessment | Characteristics of Technology / Variety / Product / Enterprise | Farming / Enterprise Situation | No. of trials | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Raisen | 2018 | Kharif | 30% losses in pulses during storage. | Assessment of grain pro super bag for storage of pulses by farm women T1: Gunny bag. T2: Grain pro super bag | Assess. | Income Generation | Grain pro super bag for storage of pulses. | Pulses | Irrigated | 05 | - |
| Raisen | 2018 | Kharif | Low efficiency and improper seed treatment | Assessment of seed treating drum for drudgery reduction among farm women in soybean crop. T1: Manual seed treatment. T2: Effective seed treatment through seed treating drum with improved efficiency. | Assess. | Drudgery reduction | Effective seed treatment through seed treating drum with improved efficiency. | Soybean | Rainfed | 05 | - |
| Raisen | 2018-19 | Rabi | Low income of farm women due to improper management of bio-waste | Assessment of vermi compost production unit for income generation. T1: Low income of farm women due to improper management of bio-waste. T2: Vermicompost | Assess. | Income Generation | Vermicompost | Vermicompost | Irrigated | 05 | - |
| Raisen | 2018-19 | Rabi | High mortality of seed during seedling preparation & low income of farm women during vegetable production | Assessment of Pro –Tray for Vegetable seedling. T1: Traditional practice of preparation of vegetable seedling. T2: Pro-tray. | Assess. | Income Generation | Pro-Tray | Pro-Tray | Irrigated | 05 | - |

2.11 (A) Economic Performance Home Science OFT: (For Drudgery Reduction)

| KVK name | OFT Title |  |  |  |  |  |  |  |  | Performance Indicator / Parameter |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Output m2/h |  |  | Est. Energy Expenditure kj/min. |  |  |  | WHR beat/min |  |  | % reduction in drudgery |  | % increase in efficiency |  | Cardiac Cost of Work |  | % Saving of cardiac Cost |  |
|  |  | T1 | T2 |  | T1 |  | T2 |  | T1 |  | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 |
| Raisen | Assessment of seed treating drum for drudgery reduction among farm women in soybean crop. T1: Manual seed treatment. T2: Effective seed treatment through seed treating drum with improved efficiency. | 75 | 186 |  | 9.76 |  | 6.39 |  | 115.23 |  | 94.00 | - | 18.24 | - | 133.33 | 40.2 | 19.0 | - | 47.26 |

2.11(B) Economic Performance Home Science OFT: (For Income Generation)

| KVK name | OFT Title | Performance Indicator / Parameter |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Production per unit |  | Cost of input |  | Incremental income |  | Yield(Kg/ha) |  | Net Return |  | Saving in Rs | BC ratio |
|  |  | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 |  |  |
| Raisen | Assessment of grain pro super bag for storage of pulses by farm women. | - | - | 20000 | 25355 | 82830 | 118500 | 11.00 | 15.8 | 63598 | 99200 | 29547 | 4.67 |
| Raisen | Assessment of vermi compost production unit for income generation. | - | - | - | 1000 | 294.3 | 2471.0 | 146.2 | 493.8 | - | 1471 | 471 | 2.17 |
| Raisen | Assessment of Pro –Tray for Vegetable seedling. | 13790.8 | 9349.8 | 4850 | 3720 | 6895.7 | 28049.4 | - | - | 2045.7 | 24929.4 | 20609.4 | 7.53 |

2.11 (C) Economic Performance Home Science OFT: (For value addition)

| KVK name | OFT Title | Performance Indicator / Parameter |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Composition of product |  | Input used |  | outcome (Kg) |  | Cost of input |  | Incremental income |  | Net Return |  | Saving in Rs | BC ratio |
|  |  | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 |  |  |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |

2.11(D)   Economic Performance Home Science OFT: (For Nutritional security)

| KVK name | OFT Title | Performance Indicator / Parameter |  |  |  | Nutrient Intake (Unit) |  |  |  |  |  |  |  | Anthropometric measurements |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Name of vegetable/Fruit/Product |  | Per capita Consumption gm/ day |  | Energy (kcal) |  | Protein (gm) |  | Iron (mg) |  | Calcium (mg) |  | Increase in Weight (Kg) |  | Increase in Height (cm ) |  | Increase in BMI (%) |  |
|  |  | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |

  - Feedback from KVK to Research System

| Name of KVK | Feedback |
| --- | --- |
| - | - |

3.	Achievements of Frontline Demonstrations (FLD)

3.1. Follow-up for results of FLDs implemented during previous years

List of technologies demonstrated and popularized during previous years and recommended for large scale adoption in the district

| KVK Name | Crop/ Enterprise | Thematic Area | Technology demonstrated | Details of popularization methods suggested to the Extension system | Horizontal spread of technology |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | No. of villages | No. of farmers | Area in ha |
| Raisen | Soybean | ICM | Improved variety 20-69 + CMP | Training, Field Day, FLD | 25 | 175 | 225 |
| Raisen | Blackgram | ICM | Improved variety PU-31 + CMP | Training, Field Day, FLD | 17 | 210 | 360 |
| Raisen | Pigeonpea | ICM | Improved variety TJT-501 + CMP | Training, Field Day, FLD | 210 | 1275 | 2200 |
| Raisen | Chickpea | ICM | Improved variety JG-63 + CMP | Training, Field Day, FLD | 35 | 205 | 345 |

  - Details of FLDs on Crop to be implemented during  2018-19

| KVK Name | year | Season | Thematic area | Technology demonstrated | Name of Crop/ Enterprise | Name of Variety/Technology/Enterprises | Crop- Area (ha) / Entrep - No. | Results (q/ha) |  | % change | No. of farmers |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | FP (T1) | RP (T2) |  | SC | ST | Others | General | Total |
| CFLD under NFSM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Raisen | 2018 | Kharif | ICM | Demonstration on Integrated Crop Management in Soybean. | Soybean | JS 20-29/JS 20-69. | 30 | - | - | - | - | - | - | - | - |
| Raisen | 2018 | Kharif | ICM | Demonstration on Integrated Crop Management in Blackgram. | Blackgram | PU-31/PU-40 | 20 | - | - | - | - | - | - | - | - |
| Raisen | 2018 | Kharif | ICM | Demonstration on Integrated Crop Management in Pigeonpea. | Pigeonpea | TJT-501 | 10 | - | - | - | - | - | - | - | - |
| Raisen | 2018-19 | Rabi | ICM | Demonstration on Integrated Crop Management in Chickpea. | Chickpea | JG-63 | 30 | - | - | - | - | - | - | - | - |
| Raisen | 2018-19 | Rabi | ICM | Demonstration on Integrated Crop Management in Lentil. | Lentil | IPL-316 | 20 | - | - | - | - | - | - | - | - |
| Raisen | 2018-19 | Rabi | ICM | Demonstration on Integrated Crop Management in Linseed. | Linseed | JLS-67 | 30 | - | - | - | - | - | - | - | - |
| FLD other than NFSM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Raisen | 2018 | Kharif | ICM | Demonstration on weed management in Blackgram (Imazathapyre + Propaquzaphop) | Blackgram | Imazathapyre + Propaquzaphop | 2/5 | 5.15 | 7.20 | 39 | - | - | 3 | 2 | 5 |
| Raisen | 2018 | Kharif | ICM | Demonstration on weed management in Soybean by pre-emergence weedicide (Diclosulam) | Soybean | Diclosulam | 2/5 | 9.05 | 12.11 | 34 | - | - | 2 | 3 | 5 |
| Raisen | 2018-19 | Rabi | ICM | Sulfosulfuron + Metsulfuron for weed control in Wheat | Wheat | Sulfosulfuron + Metsulfuron | 2/5 | 37.25 | 44.75 | 20 | - | - | 4 | 1 | 5 |
| Raisen | 2018 | Kharif | IDM | Management of Rhizoctonia rot in Soybean. (Trichoderma viride) | Soybean | Trichoderma viride | 2/5 | 6.95 | 9.20 | 32 | - | - | 5 | - | 5 |
| Raisen | 2018 | Kharif | IDM | Management of Yellow mosaic in Blackgram (Imidaclorprid 48 FS + Trizophos 40 EC) | Blackgram | Trichoderma viride | 2/5 | 4.85 | 6.90 | 42 | - | - | 3 | 2 | 5 |
| Raisen | 2018 | Kharif | IPM | Management of girdle beetle in Soybean (Thiacloprid 21.7 SC) | Soybean | Thiacloprid 21.7 SC | 2/5 | 8.75 | 10.25 | 17 | - | - | 2 | 3 | 5 |
| Raisen | 2018-19 | Rabi | INM | Demonstration of Liquid Bio-fertilizer in chickpea (Rhizobium + PSB). | Chickpea | Rhizobium + PSB | 2/5 | 15.25 | 17.75 | 16.39 | - | - | 10 | - | 10 |
| Raisen | 2018 | Kharif | INM | Demonstration of Bentonite Sulphur in Soybean | Soybean | Bentonite Sulphur | 2/5 | 11.87 | 13.52 | 19.64 | - | - | 2 | 3 | 5 |
| Raisen | 2018 | Kharif | INM | Demonstration of Potassium with STV based nutrient management in Rice. | Rice | STV based NPK & Zinc. | 2/5 | 46.8 | 51.5 | 10.04 | - | - | 5 | - | 5 |
| Raisen | 2018 | Kharif | HOF-VE | Demonstration of Marigold (Pusa Narangi) | Marigold | Pusa Narangi | 10 | 30.81 | 74.52 | 141.00 | 2 | 4 | 2 | 2 | 10 |
| Raisen | 2018-19 | Rabi | HOV-VE | Demonstration of Improved variety of Garlic (G-82) | Garlic | G-82 | 5 | 78.81 | 134.51 | 70.67 | 2 | 1 | 1 | 1 | 5 |

3.3 Economic Impact of FLD

| KVK Name | Technology demonstrated | Name of Crop/ Enterprise | Parameters |  |  | Cost of cultivation (Rs/ha) |  | Gross Return (Rs/ha) |  | Average Net Return (Rs/ha) |  | Benefit-Cost Ratio (Gross Return / Gross Cost) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Name and unit of Parameter | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) |
| Raisen | Demonstration on weed management in Blackgram (Imazathapyre + Propaquzaphop) | Blackgram | Weed density/ (sqm) | 80.45 | 12.5 | 12200 | 13400 | 20600 | 28200 | 8400 | 15400 | 1.68 | 2.14 |
| Raisen | Demonstration on weed management in Soybean by pre-emergence weedicide (Diclosulam) | Soybean | Weed density/ (sqm) | 65.5 | 7.5 | 12500 | 13500 | 22625 | 30375 | 10125 | 16875 | 1.81 | 2.25 |
| Raisen | Sulfosulfuron + Metsulfuron for weed control in Wheat | Wheat | Weed density/ (sqm) | 47.5 | 14.5 | 31500 | 32500 | 74500 | 89500 | 43000 | 57000 | 2.36 | 2.75 |
| Raisen | Management of Rhizoctonia rot in Soybean. (Trichoderma viride) | Soybean | Disease incidence (%) | 12-15 | 4-5 | 14500 | 15300 | 17375 | 23000 | 2875 | 7700 | 1.19 | 1.50 |
| Raisen | Management of Yellow mosaic in Blackgram (Imidaclorprid 48 FS + Trizophos 40 EC) | Blackgram | Disease incidence (%) | 10-12 | 3-4 | 11750 | 12500 | 19400 | 27600 | 7650 | 15100 | 1.65 | 2.20 |
| Raisen | Management of girdle beetle in Soybean (Thiacloprid 21.7 SC) | Soybean | Effected plant/meter (No.) | 5.7 | 1.3 | 11500 | 12200 | 21875 | 25625 | 10375 | 13425 | 1.90 | 2.10 |
| Raisen | Demonstration of Liquid Bio-fertilizer in chickpea (Rhizobium + PSB). | Chickpea | Pods/plant (No.) | 23.5 | 35.5 | 17500 | 17800 | 68625 | 79875 | 51125 | 62075 | 3.92 | 4.49 |
| Raisen | Demonstration of Bentonite Sulphur in Soybean | Soybean | Pods/plant (No.) | 31.67 | 35.76 | 21250 | 22250 | 35610 | 40560 | 14360 | 18310 | 1.66 | 1.82 |
| Raisen | Demonstration of Potassium with STV based nutrient management in Rice. | Rice | Tillers/plant (No.) | 17 | 22 | 48165 | 48965 | 117000 | 128750 | 68835 | 79785 | 2.43 | 2.63 |
| Raisen | Demonstration of Marigold (Pusa Narangi) | Marigold | Flowers/plant (No.) | 18.31 | 27.51 | 18235 | 24450 | 61620 | 149040 | 43385 | 124590 | 3.37 | 6.09 |
| Raisen | Demonstration of Improved variety of Garlic (G-82) | Garlic | Bulb Weight (gm) | 27.08 | 34.26 | 60567 | 78831 | 118215 | 201765 | 57668 | 122934 | 1.95 | 2.55 |

  - Details of FLDs on Agriculture Engineering to be implemented during  2018-19

| KVK Name | year | Season | Thematic area | Technology demonstrated | Name of Crop/ Enterprise | Name of Variety/Technology/Enterprises | Crop- Area (ha) / Entrep - No. | Results (q/ha) |  | % change | No. of farmers |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | FP (T1) | RP (T2) |  | SC | ST | Others | General | Total |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |

3.5    Economic Impact of FLD

| KVK Name | Technology demonstrated | Name of Crop/ Enterprise | Parameters |  |  | Cost of cultivation (Rs/ha) |  | Gross Return (Rs/ha) |  | Average Net Return (Rs/ha) |  | Benefit-Cost Ratio (Gross Return / Gross Cost) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Name and unit of Parameter | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - |

  - Details of FLDs on Animal Science to be implemented during  2018-19

| KVK Name | year | Season | Thematic area | Technology demonstrated | Name of Crop/ Enterprise | Name of Variety/Technology/Enterprises | Crop- Area (ha) / Entrep - No. | Results (q/ha) |  | % change | No. of farmers |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | FP (T1) | RP (T2) |  | SC | ST | Others | General | Total |
| Raisen | 2018 | Kharif | AS | Mineral Salt lick in lactating Buffaloes | Livestock | Mineral Salt lick | 10 | 5.5 | 6.8 | 23.63 | 0 | 0 | 10 | 0 | 10 |
| Raisen | 2018-19 | Rabi | AS | Methochelated oral calcium supplementation on milk production in dairy buffaloes. | Oral Calcium | Oral Calcium | 10 | 6.5 | 8 | 23 | 0 | 0 | 10 | 0 | 10 |
| Raisen | 2018-19 | Rabi | AS | Demonstration of Vitamin E and Selenium in Buffalo. | Livestock | Vitamin E & Selenium | 10 | 1 | 4 | 75 | 0 | 5 | 0 | 0 | 5 |

3.7       Economic Impact of FLD

| KVK Name | Technology demonstrated | Name of Crop/ Enterprise | Parameters |  |  | Cost of cultivation (Rs/ha) |  | Gross Return (Rs/ha) |  | Average Net Return (Rs/ha) |  | Benefit-Cost Ratio (Gross Return / Gross Cost) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Name and unit of Parameter | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) |
| Raisen | Mineral Salt lick in lactating Buffaloes | Livestock | Kg | 15.65 | 18.55 | 130 | 135 | 264 | 327 | 134 | 192 | 1.11 | 1.41 |
| Raisen | Methochelated oral calcium supplementation on milk production in dairy buffaloes. | Oral Calcium | Kg | 15.45 | 18.65 | 150 | 165 | 325 | 400 | 175 | 235 | 1.16 | 1.42 |
| Raisen | Demonstration of Vitamin E and Selenium in Buffalo. | Livestock | No of animals in post partem heat | 1 | 4 | 700 | 750 | 2212 | 2428 | 1512 | 1678 | 2.16 | 2.24 |

  - Details of FLDs on Fishery to be implemented during  2018-19

| KVK Name | year | Season | Thematic area | Technology demonstrated | Name of Crop/ Enterprise | Name of Variety/Technology/Enterprises | Crop- Area (ha) / Entrep - No. | Results (q/ha) |  | % change | No. of farmers |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | FP (T1) | RP (T2) |  | SC | ST | Others | General | Total |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |

3.9        Economic Impact of FLD

| KVK Name | Technology demonstrated | Name of Crop/ Enterprise | Parameters |  |  | Cost of cultivation (Rs/ha) |  | Gross Return (Rs/ha) |  | Average Net Return (Rs/ha) |  | Benefit-Cost Ratio (Gross Return / Gross Cost) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Name and unit of Parameter | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) | FP (T1) | RP (T2) |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - |

  - Details of FLDs on Agriculture Extension to be implemented during  2018-19

| KVK Name | Season & Year | Problem identified | Title | Thematic Area | Source of Technology (Year) | Detail of Technology Demonstrated | Area (ha) | FP (T1) | RP (T2) | Variety | No. of Village | No of Demonstration | No. of farmers |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  | SC | ST | Others | General | Total |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |

3.11 Impact of FLD

| KVK Name | Name of parameter |  |  | Data on the parameter |  |  | Result | Feedback from the farmer |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 1 | 2 | 3 |  |  |
| Raisen | - | - | - | - | - | - | - | - |

3.12 Information about Home Science FLDs - (For All Thematic Area)

| KVK name | Year | Season | Thematic Area | Problem Identified | Technology to be Demonstrated as Solution to the Identified Problem | Crop/ Enterprise (In which crop Enterprise or Farming Activity) | Name of Variety/Technology/Entreprizes | Farming Situation | Proposed area (ha) | No. of Beneficiaries |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Raisen | 2018 | Kharif | WA | Low work efficiency and high drudgery of farm women during weeding of paddy crop. | Demonstration of Cono weeder in paddy crop | Paddy | Cono weeder | - | 2 | 5 |
| Raisen | 2018 | Kharif | WA | Low work efficiency and high drudgery of farm women during grading of pigeonpea. | Demonstration of Spiral seed grader in Pigeonpea | Pigeonpea | Spiral Grader | - | 2 | 5 |
| Raisen | 2018-19 | Rabi | WA | Low work efficiency and high drudgery of farm women during weeding of vegetable crop. | Demonstration of Twin –wheel hoe in vegetable crops. | Vegetables | Twin –wheel hoe | - | 2 | 5 |
| Raisen | 2018-19 | Rabi | WA | Low health status of farm women due to absence of vegetable in diet | Demonstration of Performance of Nutritional kitchen gardening. | Vegetables | Vegetable crops. | - | 2 | 5 |

3.12 (A) Economic Performance Home Science FLD: (For Drudgery Reduction)

| KVK name | FLD Title |  |  |  |  |  |  |  |  | Performance Indicator / Parameter |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Output m2/h |  |  | Est. Energy Expenditure kj/min. |  |  |  | WHR beat/min |  |  | % reduction in drudgery |  | % increase in efficiency |  | Cardiac Cost of Work |  | % Saving of cardiac Cost |  |
|  |  | T1 | T2 |  | T1 |  | T2 |  | T1 |  | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 |
| Raisen | Demonstration of Cono weeder in paddy crop | 60.3 | 120.63 |  | 9.46 |  | 5.26 |  | 115.3 |  | 95.36 | - | 44.39 | - | 100.04 | 38.13 | 21.56 | - | 56.56 |
| Raisen | Demonstration of Spiral seed grader in Pigeonpea | 80 | 230.36 |  | 8.65 |  | 6.19 |  | 105.69 |  | 94.65 | - | 28.43 | - | 187.95 | 32.52 | 15.36 | - | 54.61 |
| Raisen | Demonstration of Twin –wheel hoe in vegetable crops. | 61.6 | 140.23 |  | 13.23 |  | 7.39 |  | 113.85 |  | 98.36 | - | 44.14 | - | 127.64 | 57.85 | 25.36 | - | 43.81 |

3.12 (B) Economic Performance Home Science FLD: (For Income Generation)

| KVK name | OFT Title | Performance Indicator / Parameter |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Production per unit |  | Cost of input |  | Incremental income |  | Yield(Kg/ha) |  | Net Return |  | Saving in Rs | BC ratio |
|  |  | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 |  |  |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - |

3.12 (C) Economic Performance Home Science FLD: (For value addition)

| KVK name | OFT Title | Performance Indicator / Parameter |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Composition of product |  | Input used |  | outcome (Kg) |  | Cost of input |  | Incremental income |  | Net Return |  | Saving in Rs | BC ratio |
|  |  | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 |  |  |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |

3.12 (D)   Economic Performance Home Science FLD: (For Nutritional security)

| KVK name | FLD Title | Performance Indicator / Parameter |  |  |  | Nutrient Intake (Unit) |  |  |  |  |  |  |  | Anthropometric measurements |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Name of vegetable/Fruit/Product |  | Per capita Consumption gm/ day |  | Energy (kcal) |  | Protein (gm) |  | Iron (mg) |  | Calcium (mg) |  | Increase in Weight (Kg) |  | Increase in Height (cm ) |  | Increase in BMI (%) |  |
|  |  | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 | T1 | T2 |
| Raisen | Demonstration of Performance of Nutritional kitchen | Vegetable crops | Vegetable crops | 104 | 300 | 7.214 | 17.04 | 2.288 | 6.014 | 4.55 | 2.69 | 13.23 | 30.24 | 1.5 | 4.3 | 1.0 | 5.0 | 3.36 | 3.0 |

3.13 Training and Extension activities proposed under FLD

| KVK Name | Crop | Activity | No. of activities organized | Number of participants | Remarks |
| --- | --- | --- | --- | --- | --- |
| Raisen | Paddy | Field day | 1 | 17 | Conoweeder |

3.14 Details of FLD on crop hybrids.

| S. No. | Name of the KVK | Name of the Crop | Name of the Hybrids | Source of Hybrid (Institute/Firm) | No. of farmers | Area in ha. |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Raisen | - | - | - | - | - |

4. Feedback System

4.1. Feedback of the Farmers to KVK

| Name of KVK | Feedback |  |  |  |
| --- | --- | --- | --- | --- |
|  | Technology appropriations | Methodology used | Benefits of OFT/FLD | Future Adoption |
| Raisen | Technology appreciated by farmer | Improve variety of Soybean JS 20-69. | Soybean variety performs well in all areas. | Greater possibility of future adoption. |
| Raisen | Technology appreciated by farmer | Improve variety of Chickpea JG-63. | Significantly increase the seed yield as well as wilt resistant. | Greater possibility of future adoption. |
| Raisen | Technology appreciated by farmer | Improve variety of Pigeonpea TJT-501. | Medium duration variety of Pigeonpea performed well. | Greater possibility of future adoption. |

4.2. Feedback from KVK to Research System.

| Name of KVK | Feedback basic of OFT on Technology Tested |
| --- | --- |
| Raisen | Need to develop charcoal rot & collar rot resistant variety of Soybean. |
| Raisen | Need to develop Yellow mosaic resistant variety of Black gram. |
| Raisen | Need to develop False smut & Sheath blight resistant variety of Rice. |
| Raisen | Need to develop short duration variety of Pigeonpea. |

4. Documentation of the need assessment conducted by the KVK for the training programme

| Name of KVK | Category of the training | Methods of need assessment | Date and place | No. of participants involved |
| --- | --- | --- | --- | --- |
| Raisen | Vocational | Group Discussion- During the Group Discussion farmers have interested of training on IPM in paddy production | 10th February 2018 Bhanpurgarhi (Gairatganj) | 22 |
| Raisen | Vocational | Group Discussion – During the Group Discussion farmers/farmwomen have interested on training on summer vegetable | 20th February 2018 Dehgaon (Gairatganj) | 25 |
| Raisen | Rural Youth | Group Discussion – During the Group Discussion rural youth have interested of training on organic farming. | 10th January, 2018 Genhuras | 20 |

Abbreviation Used

| FW | (A) Farmers & Farm Women |
| --- | --- |
| RY | (B) Rural Youths |
| IS | (C) Extension Personnel |
| ONC | On Campus Training Programme |
| OFC | Off Campus Training Programme |
| M | Male |
| F | Female |
| T | Total |
| Thematic Areas for Training |  |
| CRP | Crop Production |
| HOV | Horticulture – Vegetable Crops |
| HOF | Horticulture-Fruits |
| HOO | Horticulture- Ornamental Plants |
| HOP | Horticulture- Plantation crops |
| HOT | Horticulture- Tuber crops |
| HOS | Horticulture- Spices |
| HOM | Horticulture- Medicinal and Aromatic Plants |
| SFM | Soil Health and Fertility Management |
| LPM | Livestock Production and Management |
| WOE | Home Science/Women empowerment |
| AEG | Agril. Engineering |
| PLP | Plant Protection |
| FIS | Fisheries |
| PIS | Production of Inputs at site |
| CBD | Capacity Building and Group Dynamics |
| AGF | Agro-forestry |
| OTH | Others |

5.	TRAINING PROGRAMMES

1.	Training programmes should be strictly covered under above mentioned thematic areas only,

2.	For category, training type and thematic area, mention code/abbreviations only

Table  5.1. Details of Training  programmes conducted by the KVKs for Farmers

| Name of KVK | Category (F &FW/FW) | Training Type (ONC/ OFC) | Thematic Area of training | Training Title | No. of Courses | Duration (Days) | Participants |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Gen |  | SC |  | ST |  | Others |  |
|  |  |  |  |  |  |  | M | F | M | F | M | F | M | F |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |
| Raisen | F & FW | OFC | CRP | Soybean production technology | 1 | 1 | 12 | - | 3 | - | - | - | 6 | - |
| Raisen | F & FW | ONC | CRP | Soybean production technology | 1 | 1 | 3 | - | 1 | - | 1 | - | 20 | - |
| Raisen | F & FW | ONC | CRP | Blackgram production technology | 1 | 1 | 5 | - | 1 | - | 1 | - | 18 | - |
| Raisen | F & FW | ONC | CRP | Gram production technology | 1 | 1 | 10 | - | 1 | - | - | - | 8 | - |
| Raisen | F & FW | ONC | CRP | Wheat production technology | 1 | 1 | 7 | - | 6 | - | 1 | - | 5 | - |
| Raisen | F & FW | ONC | CRP | ICM practice in Rabi crop | 1 | 1 | - | - | 2 | - | - | - | 18 | - |
| Raisen | F & FW | ONC | CRP | ICM in rabi crops | 1 | 1 | 3 | - | - | - | 4 | - | 10 | - |
| Raisen | F & FW | OFC | CBD | Leadership Development | 1 | 1 | 16 | - | 1 | - | 1 | - | - | - |
| Raisen | F & FW | ONC | CBD | Strategical plan for production of kharif crops | 1 | 1 | 7 | - | 1 | - | - | - | 10 | - |
| Raisen | F & FW | ONC | CBD | Leadership development | 1 | 1 | 8 | - | - | - | - | - | 10 | - |
| Raisen | F & FW | OFC | HOV | Nursery raising technology of vegetable crops. | 1 | 1 | 8 | - | 3 | - | - | - | 8 | - |
| Raisen | F & FW | OFC | HOF | Care & maintenance of fruit orchard. | 1 | 1 | 15 | - | - | - | - | - | 12 | - |
| Raisen | F & FW | OFC | HOV | Vegetables production technique | 1 | 1 | 10 | - | 4 | - | - | - | 10 | - |
| Raisen | F & FW | OFC | HOV | Nursery raising technology in vegetables crop | 1 | 1 | 7 | - | 3 | - | - | - | 12 | - |
| Raisen | F & FW | OFC | HOV | Production technology of Rabi vegetables | 1 | 1 | 5 | - | 1 | - | 5 | - | 10 | - |
| Raisen | F & FW | OFC | HOV | Vegetable production technology | 1 | 1 | - | - | 6 | - | - | - | 19 | - |
| Raisen | F & FW | OFC | HOV | Nursery raising technology | 1 | 1 | - | - | 4 | - | 8 | - | 6 | - |
| Raisen | F & FW | OFC | HOV | Nursery raising technology of vegetable crops | 1 | 1 | - | - | 1 | - | 14 | - | 4 | - |
| Raisen | F & FW | OFC | HOS | Seed production of spices crops | 1 | 1 | - | - | - | - | 21 | - | 3 | - |
| Raisen | F & FW | OFC | HOS | Cultivation of Summer vegetables | 1 | 1 | - | - | - | - | 13 | - | 6 | - |
| Raisen | F & FW | ONC | HOV | Nursery raising technology for vegetable crops | 1 | 1 | 6 | - | - | - | - | - | 14 | - |
| Raisen | F & FW | ONC | HOF | Planting material production of fruit crops | 1 | 1 | 4 | - | - | - | 2 | - | 10 | - |
| Raisen | F & FW | ONC | HOV | Improved production technology of vegetables | 1 | 1 | 10 | - | - | - | - | - | 10 | - |
| Raisen | F & FW | OFC | PLP | IDM in Kharif crops | 1 | 1 | 21 | - | 1 | - | - | - | - | - |
| Raisen | F & FW | OFC | PLP | IPM in Rice | 1 | 1 | 17 | - | - | - | - | - | - | - |
| Raisen | F & FW | OFC | PLP | IPM & IDM in Rice | 1 | 1 | 12 | - | 3 | - | - | - | 12 | - |
| Raisen | F & FW | OFC | PLP | IDM in Rice | 1 | 1 | 1 | - | 2 | - | - | - | 20 | - |
| Raisen | F & FW | OFC | PLP | Seed treatment in pulse crops | 1 | 1 | 9 | - | 2 | - | - | - | 6 | - |
| Raisen | F & FW | OFC | PLP | Disease management in pulse crops | 1 | 1 | 5 | - | 3 | - | - | - | 10 | - |
| Raisen | F & FW | OFC | PLP | Insect & Pest management in Rabi crops | 1 | 1 | - | - | - | - | 23 | 4 | - | - |
| Raisen | F & FW | OFC | PLP | Disease management in Rabi crops | 1 | 1 | 6 | - | 3 | - | 4 | - | 10 | - |
| Raisen | F & FW | OFC | PLP | IPM in pulse crop | 1 | 1 | 1 | - | 1 | - | 17 | - | - | - |
| Raisen | F & FW | OFC | PLP | Pest management in Oilseed | 1 | 1 | - | - | 1 | - | 21 | - | - | - |
| Raisen | F & FW | ONC | PLP | Seed treatment in kharif crops | 1 | 1 | 3 | - | 2 | - | 5 | - | 7 | - |
| Raisen | F & FW | ONC | PLP | IPM in kharif crops | 1 | 1 | 4 | - | - | - | - | - | 16 | - |
| Raisen | F & FW | ONC | PLP | Mushroom production technology | 1 | 1 | 15 | - | 5 | - | - | - | 10 | - |
| Raisen | F & FW | ONC | PLP | IDM in Kharif crops | 1 | 1 | 10 | - | 4 | - | - | - | 7 | - |
| Raisen | F & FW | ONC | PLP | IPM in Kharif crops | 1 | 1 | 8 | - | - | - | - | - | 10 | - |
| Raisen | F & FW | ONC | PLP | Wilt management in pulse crops | 1 | 1 | 6 | - | 1 | - | 6 | - | 7 | - |
| Raisen | F & FW | ONC | PLP | IPM in pulses | 1 | 1 | 10 | - | 1 | - | 1 | - | 14 | - |
| Raisen | F & FW | ONC | PLP | IDM in pulses | 1 | 1 | 5 | - | 2 | - | - | - | 12 | - |
| Raisen | F & FW | ONC | PLP | Honeybee production technology | 1 | 1 | - | - | - | - | - | - | - | - |
| Raisen | F & FW | OFC | LPM | Livestock nutrition & management. | 1 | 1 | - | - | - | - | - | - | 18 | - |
| Raisen | F & FW | OFC | LPM | Goat rearing & Management | 1 | 1 | 10 | - | 2 | - | - | - | 5 | - |
| Raisen | F & FW | OFC | LPM | Animal feed management | 1 | 1 | 11 | - | 3 | - | - | - | 7 | - |
| Raisen | F & FW | ONC | LPM | Dairy Management | 1 | 1 | 5 | - | 1 | - | 5 | - | 7 | - |
| Raisen | F & FW | ONC | LPM | Animal Disease Management. | 1 | 1 | 10 | - | - | - | - | - | 7 | - |
| Raisen | F & FW | ONC | LPM | Fish production technology. | 1 | 1 | 14 | - | 2 | - | - | - | 10 | - |
| Raisen | F & FW | ONC | LPM | Disease management in Animals | 1 | 1 | 10 | - | - | - | - | - | 10 | - |
| Raisen | F & FW | ONC | LPM | Dairy management | 1 | 1 | 8 | - | 1 | - | 3 | - | 8 | - |
| Raisen | F & FW | ONC | LPM | Goat rearing | 1 | 1 | - | - | - | - | 5 | - | 10 | - |
| Raisen | F & FW | OFC | SFM | Importance of Soil Testing | 1 | 1 | 4 | - | 4 | - | - | - | 12 | - |
| Raisen | F & FW | OFC | SFM | Soil & Water conservation | 1 | 1 | 11 | - | - | - | - | - | 9 | - |
| Raisen | F & FW | OFC | SFM | Awareness & training of fast microbial decomposer | 1 | 1 | 2 | - | 5 | - | 7 | - | 3 | - |
| Raisen | F & FW | OFC | SFM | Awareness & training of fast microbial decomposer | 1 | 1 | 10 | - | 1 | - | 2 | - | 10 | - |
| Raisen | F & FW | OFC | SFM | Nutrient management in Rice crop | 1 | 1 | 20 | - | 3 | - | - | - | - | - |
| Raisen | F & FW | OFC | SFM | Use of waste decomposer for manure making | 1 | 1 | 10 | - | 3 | - | - | - | 8 | - |
| Raisen | F & FW | OFC | SFM | Importance of Bio-fertilizer in legume’s crop | 1 | 1 | 8 | - | - | - | - | - | 10 | - |
| Raisen | F & FW | OFC | SFM | INM in Wheat | 1 | 1 | - | - | 2 | - | 1 | - | 23 | - |
| Raisen | F & FW | OFC | SFM | Importance of Waste decomposer in agriculture waste decomposition. | 1 | 1 | 8 | - | - | - | 1 | - | 20 | - |
| Raisen | F & FW | OFC | SFM | Soil fertility management | 1 | 1 | 7 | - | 3 | - | - | - | 16 | - |
| Raisen | F & FW | ONC | SFM | Soil testing & fertility management in kharif crops | 1 | 1 | 4 | - | 2 | - | 6 | - | 6 | - |
| Raisen | F & FW | ONC | SFM | INM in vegetables | 1 | 1 | 4 | - | - | - | 3 | - | 10 | - |
| Raisen | F & FW | ONC | SFM | INM in Wheat | 1 | 1 | 5 | - | - | - | - | - | 10 | - |
| Raisen | F & FW | ONC | SFM | Micronutrient in Wheat crop | 1 | 1 | - | - | 2 | - | - | - | 18 | - |
| Raisen | F & FW | ONC | SFM | Micronutrient management in vegetable crops | 1 | 1 | 6 | - | - | - | 7 | - | 14 | - |
| Raisen | F & FW | ONC | SFM | Use of Bio-waste decomposer | 1 | 1 | - | - | - | - | - | - | 20 | - |
| Raisen | FW | OFC | WOE | Women Empowerment through SHG’s | 1 | 1 | - | - | - | - | - | - | - | 21 |
| Raisen | FW | OFC | WOE | Awareness programme for goat farming | 1 | 1 | - | 4 | - | 6 | - | - | - | 8 |
| Raisen | FW | OFC | WOE | Food processing for rural women. | 1 | 1 | - | 7 | - | - | - | - | - | 10 |
| Raisen | FW | OFC | WOE | Storage technology for crops | 1 | 1 | - | - | - | 16 | - | 2 | - | 5 |
| Raisen | FW | OFC | WOE | Value addition | 1 | 1 | - | - | - | 8 | - | 15 | - | 2 |
| Raisen | FW | OFC | WOE | Income generation through nursery raising | 1 | 1 | - | - | - | - | - | - | - | 26 |
| Raisen | FW | OFC | WOE | Mushroom production | 1 | 1 | - | - | - | - | - | - | - | 16 |
| Raisen | FW | OFC | WOE | Use of Agricultural waste material for fuel making | 1 | 1 | - | - | - | 16 | - | 11 | - | 4 |
| Raisen | FW | OFC | WOE | Food processing for self employment | 1 | 1 | - | - | - | 12 | - | - | - | 24 |
| Raisen | FW | ONC | WOE | Nursery raising management in paddy crops | 1 | 1 | - | 6 | - | 11 | - | - | - | 6 |
| Raisen | RY | OFC | WOE | Dairy farming and value addition | 1 | 5 | - | 2 | - | 18 | - | - | - | 7 |
| Raisen | RY | OFC | WOE | Backyard poultry | 1 | 5 | - | - | - | 4 | - | 5 | - | 15 |
| Raisen | RY | OFC | LPM | Fodder production & management | 1 | 5 | - | - | 1 | - | - | - | 18 | - |
| Raisen | IS | OFC | WOE | Role of Agriculture crop in Nutritional Security | 1 | 1 | - | - | - | 3 | - | 2 | - | 22 |
| Raisen | IS | ONC | WOE | Role of Agriculture crops in Nutrition | 1 | 1 | - | - | - | 10 | - | 1 | - | 9 |

Table  5.2. Details of Training  Programmes conducted by the KVKs for Rural Youth

| Name of KVK | Category (RY) | Training Type (ONC/OFC) | Thematic Area of training | No. of Courses | Duration (Days) | Participants |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Gen |  | SC |  | ST |  | Others |  |
|  |  |  |  |  |  | M | F | M | F | M | F | M | F |
| Raisen | RY | OFC | WOE | Dairy farming and value addition | 5 | - | 2 | - | 18 | - | - | - | 7 |  |
| Raisen | RY | OFC | WOE | Backyard poultry | 5 | - | - | - | 4 | - | 5 | - | 15 |  |
| Raisen | RY | OFC | LPM | Fodder production & management | 5 | - | - | 1 | - | - | - | 18 | - |  |

Table  5.3. Details of Training  Programmes conducted by the KVKs for Extension Personnel

| Name of KVK | Category (IS) | Training Type (ONC/OFC) | Thematic Area of training (if other please specify name) | No. of Courses | Duration (Days) | Participants |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Gen |  | SC |  | ST |  | Others |  |
|  |  |  |  |  |  | M | F | M | F | M | F | M | F |
| Raisen | IS | OFC | WOE | Role of Agriculture crop in Nutritional Security | 1 | 1 | - | - | - | 3 | - | 2 | - | 22 |

## Table  5.4. Details of Vocational training programmes for Rural Youth conducted by the KVKs

| Name of KVK | Thematic Area |  | Training title | Name of Crop / Enterprise | Identified Thrust Area | No of Courses | Duration of training (days) | Number of Beneficiaries |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Gen |  | SC |  | ST |  | Others |  |
|  |  |  |  |  |  |  |  | M | F | M | F | M | F | M | F |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |

Table 5.5. Sponsored Training Programmes

| Name of KVK | Title | Thematic area (as given in abbreviation table) | Sub-theme (as per column no 5 of Table T1) | Client (FW/ RY/ IS) | Dura-tion (days) | No. of courses | ###### No. of Participants |  |  |  |  |  |  |  |  | Sponsoring Agency |  | Fund received for training (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | ##### Gen |  | ##### Others |  | ##### SC |  |  | ##### ST |  |  |  |  |
|  |  |  |  |  |  |  | M | F | M | F | M | F | M |  | F |  |  |  |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - |  |

Table 5.6. Details of training programme conducted for livelihood security in rural areas by the KVKs

| Name of KVK | Training title | Self employed after training |  |  | Number of persons employed else where |
| --- | --- | --- | --- | --- | --- |
|  |  | Type of units | Number of units | Number of persons employed |  |
| Raisen | - | - | - | - | - |

Table 5.7 Training Programmes for Panchayati raj Institutions Office-bearers & members

| Name of KVK | Title | Thematic area (as given in abbreviation table) | Sub-theme (as per column no 5 of Table T1) | Client (FW/ RY/ IS) | Dura-tion (days) | No. of courses | ###### No. of Participants |  |  |  |  |  |  |  |  | Sponsoring Agency |  | Fund received for training (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | ##### Gen |  | ##### Others |  | ##### SC |  |  | ##### ST |  |  |  |  |
|  |  |  |  |  |  |  | M | F | M | F | M | F | M |  | F |  |  |  |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - |  |

Table 5.8   Evaluation/Follow up & Impact of the training programmes conducted by the KVK (all types of trainings)

| Name of KVK | Title of the training | No. of trainees | Change in knowledge (Score) |  | Change in Production (q/ha) |  | Change in Income (Rs) |  | Impact on - Area expanded (ha) - No. of farmers adopted (no.) - % change in knowledge, production & Income |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Before | After | Before | After | Before | After |  |
| Raisen | Wheat production technology | 19 | 7.65 | 11.25 | 35.50 | 42.50 | 10500 | 17500 | 1. 2. Out of 19 trainees 14 farmers adopted the recommended Wheat production technology. 3. Knowledge- 41.2%, Production- 19.71%, Income- 66% |
| Raisen | Pest management in Chickpea | 22 | 8.12 | 12.25 | 9.75 | 14.50 | 15500 | 21500 | 1. 2. Out of 22 trainees 18 farmers adopted the recommended Wheat production technology. 3. Knowledge- 45%, Production- 48.7%, Income- 38% |

6. EXTENSION ACTIVITIES

| Name of the KVK | Activity | No. of activities (Targeted) | No. of activities (Achieved) | Detail of Participants |  |  |  |  |  | Remarks |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Farmers (Others) |  | SC/ST (Farmers) |  | Extension Officials |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Purpose | Topic s | Crop Stages |
|  |  |  |  | M | F | M | F | M | F |  |  |  |
| Raisen | Advisory Services | 50 | 43 | Mass | - | - | - | - | - | - | - | - |
| Raisen | Agri mobile clinic | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Animal Health Camp | 1 | - | - | - | - | - | - | - | - | - | - |
| Raisen | Awareness programme | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Celebration of important days | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Diagnostic visits | 2 | 2 | 25 | - | 15 | - | - | - | - | - | - |
| Raisen | Exhibition | 2 | 2 | 1200 | 200 | 50 | 25 | 75 | - | - | - | - |
| Raisen | Exposure visits | 1 | - | - | - | - | - | - | - | - | - | - |
| Raisen | Extension Literature | 4 | 4 | Mass | - | - | - | - | - | - | - | - |
| Raisen | Ex-trainees Sammelan | 1 | 1 | - | 22 | - | 3 | - | - | - | - | - |
| Raisen | Farm advisory Services | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Farm Science Club conveners meet | 1 | - | - | - | - | - | - | - | - | - | - |
| Raisen | Farmers Seminar/Workshop | 2 | - | - | - | - | - | - | - | - | - | - |
| Raisen | Farmers visit to KVK | - | - | 490 | - | 55 | - | - | - | - | - | - |
| Raisen | Field Day | 5 | 5 | 92 | 17 | 35 | - | - | - | - | - | - |
| Raisen | Film Show | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Group meetings | 1 | 1 | - | 7 | - | 22 | - | - | - | - | - |
| Raisen | Interface | 2 | 1 | 40 | - | 10 | - | - | - | - | - | - |
| Raisen | Kharif/Rabi Sammelan | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Kisan Ghosthi | 1 | 1 | 25 | - | 2 | - | - | - | - | - | - |
| Raisen | Kisan Mela | 1 | - | - | - | - | - | - | - | - | - | - |
| Raisen | Krishi Gyan Doot meet | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Krishi Mahotsav | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Lectures delivered as resource persons | 10 | 10 | Mass | - | - | - | - | - | - | - | - |
| Raisen | Mahila Mandals conveners meetings | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Method Demonstrations | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Newspaper coverage | 35 | 35 | Mass | - | - | - | - | - | - | - | - |
| Raisen | Popular articles | 15 | 15 | Mass | - | - | - | - | - | - | - | - |
| Raisen | Pradhanmantri phasal beema yojana | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Radio talks | 6 | 6 | Mass | - | - | - | - | - | - | - | - |
| Raisen | Scientific visit to farmers field | 17 | 17 | 106 | - | 78 | - | - | - | - | - | - |
| Raisen | Self Help Group conveners meetings | 1 | 1 | - | 11 | - | 11 | - | - | - | - | - |
| Raisen | Soil health Camp | 1 | - | - | - | - | - | - | - | - | - | - |
| Raisen | Soil test campaigns | 1 | - | - | - | - | - | - | - | - | - | - |
| Raisen | Summer deep ploughing campaigning | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | Technology Week Celebration | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | TV talks | 5 | 5 | Mass | - | - | - | - | - | - | - | - |
| Raisen | Workshop | - | - | - | - | - | - | - | - | - | - | - |
| Raisen | PM Live webcast to farmers (20/6/2018) | 1 | 1 | 62 | 24 | 43 | 08 | - | - | - | - | - |
| Raisen | PM Live programme for farm women & SHGs (12/7/2018) | 1 | 1 | - | 45 | - | 20 | - | - | - | - | - |
| Raisen | PM Live Kisan Samman Nidhi Programme (24/2/2019) | 1 | 1 | 142 | - | 38 | - | - | - | - | - | - |
| Raisen | International Women’s Day Celebration (8/3/2019) | 1 | 1 | - | 64 | - | 20 | - | 20 | - | - | - |
| Raisen | Nutrition Month | 1 | 1 | - | 19 | - | 6 | - | - | - | - | - |
| Raisen | Farm woman Sangosthi | 2 | 2 | - | 11 | - | 33 | - | - | - | - | - |
| Raisen | Mahila Kisan Diwas (15/10/2018) | 1 | 1 | - | 57 | - | 8 | - | - | - | - | - |
| Raisen | World Food Day | 1 | 1 | - | 29 | - | 13 | - | - | - | - | - |
| Raisen | Soil Health Day (5/12/2018) | 1 | 1 | 65 | - | 15 | - | 10 | - | - | - | - |

- Literature Developed/Published (with full title, author & reference)

7.1 KVK Newsletters

| KVK Name | Date of start | Periodicity | Number of copies printed | Number of copies distributed |
| --- | --- | --- | --- | --- |
| Raisen | January-2008 | Quarterly |  |  |
| Raisen |  | Apr-Jun, 2018 | 1000 | 1000 |
| Raisen |  | Jul-Sep, 2018 | 1000 | 1000 |
| Raisen |  | Oct-Dec, 2018 | 1000 | 1000 |
| Raisen |  | Jan-Mar, 2019 | 1000 | 1000 |

7.2 Literature developed/published

| KVK Name | Type | Title | Author’s name | Number of copies |
| --- | --- | --- | --- | --- |
| Raisen | Book | Mushroom Production | Dr. Mukul Kumar | 1000 |
| Raisen | Book | Beekeeping | Mr. Pradip Kumar Dwivedi | 1000 |
| Raisen | Book | Pulse production | Dr. Swapnil Dubey | 1000 |

7.3  Details of Electronic Media Produced

| KVK Name | Type of media (CD / VCD / DVD / Audio-Cassette) | Title of the programme | Number |
| --- | --- | --- | --- |
| Raisen | - | - | - |

8.  Production and supply of Technological products

8.1 SEED production

| KVK Name | Major group/class | Crop | Variety | Quantity (qt.) | Value (Rs.) | Provided to No. of Farmers | Expected area coverage (ha.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Raisen | Kharif-2018 | Soybean | JS 20-29 | 30.00 | - | - | - |
| Raisen | Kharif-2018 | Soybean | RVS 2001-4 | 22.50 | - | - | - |
| Raisen | Kharif-2018 | Soybean | JS 20-34 | 2.50 | - | - | - |
| Raisen | Kharif-2018 | Soybean | JS 20-69 | 64.00 | - | - | - |
| Raisen | Kharif-2018 | Soybean | JS 20-98 | 1.50 | - | - | - |
| Raisen | Kharif-2018 | Blackgram | JU-86 | 1.70 | - | - | - |
| Raisen | Kharif-2018 | Blackgram | PU-31 | 4.00 | - | - | - |
| Raisen | Kharif-2018 | Blackgram | Shekhar- 2 | 3.20 | - | - | - |
| Raisen | Kharif-2018 | Pigeonpea | TJT-501 | 5.00 | - | - | - |
| Raisen | Rabi 2018-19 | Wheat | HI- 1544 | 71.00 | - | - | - |
| Raisen | Rabi 2018-19 | Wheat | JW- 3288 | 1.00 | - | - | - |
| Raisen | Rabi 2018-19 | Wheat | HI-1531 | 9.00 | - | - | - |
| Raisen | Rabi 2018-19 | Wheat | C-306 | 7.60 | - | - | - |
| Raisen | Rabi 2018-19 | Wheat | HI-8713 | 22.80 | - | - | - |
| Raisen | Rabi 2018-19 | Wheat | HI-8737 | 17.80 | - | - | - |
| Raisen | Rabi 2018-19 | Wheat | HI- 8759 | 14.00 | - | - | - |
| Raisen | Rabi 2018-19 | Wheat | HI-1544 | 13.60 | - | - | - |
| Raisen | Rabi 2018-19 | Wheat | GW-322 | 95.20 | - | - | - |
| Raisen | Rabi 2018-19 | Chickpea | JG-16 | 53.00 | - | - | - |

8.2 Planting Material production

| KVK Name | Major group/class | Crop | Variety | Nos. | Value (Rs.) | Provided to No. of Farmers | Expected area coverage (ha.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Raisen | Seedling | Tomato | Arka Rakshak | 2000 | - | - | - |
| Raisen | Seedling | Tomato | Arka Samrat | 2000 | - | - | - |
| Raisen | Seedling | Brinjal | Kashi Taru | 1500 | - | - | - |
| Raisen | Seedling | Chilli | Kashi Anmol | 1800 | - | - | - |
| Raisen | Seedling | Cabbage | Golden Acre | 1200 | - | - | - |
| Raisen | Seedling | Cauliflower | Pusa Snow ball | 1600 | - | - | - |

8.3 Production Units (bio-agents / bio pesticides/ bio fertilizers etc.)

* Name of product should follow same pattern and spelled correct

| KVK Name | Major Group Bio agent/Bio fertilizers/Bio Pesticides | Name of the Product | Qty (In Kg) | Qty (In No) | Value (Rs.) | Provided to No. of Farmers | Expected area coverage (ha.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Raisen | Bio Agents | - | - | - | - | - | - |
| Raisen | Bio Agents | - | - | - | - | - | - |
| Raisen | Bio Fertilizer | - | - | - | - | - | - |
| Raisen | Bio Fertilizer | - | - | - | - | - | - |
| Raisen | Others (Pl Specify) | - | - | - | - | - | - |

8.4 Livestock and fisheries production

| KVK Name | Name of the animal / bird / aquatics | Breed | Type of Produce | Qty. (kg/qt./litre ) | Value (Rs.) | No. of Beneficiaries |
| --- | --- | --- | --- | --- | --- | --- |
| Raisen | - | - | - | - | - | - |

9.	Activities of Soil and Water Testing Laboratory

9.1	Details of soil samples analyzed so far	:

| KVK Name | Status of establishment of Lab | Year of establishment | Details | No. of Samples | No. of Farmers | No. of Villages | Amount realized | Soil report distributed to the farmers (Nos) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Raisen | Functional | 2014 | - | 525 | 525 | - | - | 525 |

9.2	Details of   water samples analyzed so far	:

| KVK Name | Status of establishment of Lab | Year of establishment | Details | No. of Samples | No. of Farmers | No. of Villages | Amount realized | Water report distributed to the farmers (Nos) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Raisen | - | - | - | - | - | - | - | - |

10.	Rainwater Harvesting

Training programmes conducted by using Rainwater Harvesting Demonstration Unit

| Name of KVK | Date | Title of the training course | Client (PF/RY/EF) | No. of Courses | No. of Participants including SC/ST |  |  | No. of SC/ST Participants |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Male | Female | Total | Male | Female | Total |
| Raisen | - | - | - | - | - | - | - | - | - | - |

11.	Utilization of Farmers Hostel facilities

| KVK Name | Months | Year | Title of the training course | Duration of training | No. of trainees stayed | Trainee days (days stayed) | Reason for short fall (if any) | Accommodation available (No. of beds) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Raisen | - | - | - | - | - | - | - | - |

12. Utilization of Staff Quarters facilities

| KVK Name | Year of construction | Year of allotment | No. of quarters occupied | No. of quarters vacant | Reasons for vacant quarters, if any |
| --- | --- | --- | --- | --- | --- |
| Raisen | 21/03/2008 | 01/05/2008 | 06 | - | - |

13. Details of SAC Meeting

| KVK Name | Date of SAC meeting | No. of SAC members attended | Major recommendations |
| --- | --- | --- | --- |
| Raisen | 24/8/2018 | 20 | Emphasis on crop diversification, Organic farming, Hi-tech fruit and vegetable cultivation, value addition. |

14. Status of Kisan Mobile Advisory (KVK-KMA)

| KVK Name | No. of messages sent | No. of beneficiary |  | Total Number of villages | Number of villages covered | Sponsoring agency (NIC, Farmers Portal, etc.) | Major recommendations |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Farmers | Ext. Pers. |  |  |  |  |  |
| Raisen | 43 | 48500 | 175 | 1497 | 1497 | Farmers Portal (mKisan) |  | Need based SMS on Crop production, Horticulture, Plant protection, Veterinary science, weather, awareness etc. |

15. Status of Convergence with various agricultural schemes (Central & State sponsored)

| KVK Name | Name of scheme | Name of Agency (Central/state) | Funds received (Rs.) | Activities organized | Operational Area | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Raisen | Skill development training | ASCI | 165200 | Mushroom Production Skill training | Raisen | - |
| Raisen | Skill development training | ASCI | 141200 | Beekeeper Skill training | Raisen | - |

16. Status of Revolving Funds (Rs.)

| KVK Name | Account No. | Opening balance (Rs.) | Closing balance (Rs.) | Current status (Rs.) |
| --- | --- | --- | --- | --- |
| Raisen | - | - | - | - |

17. Awards & Recognitions

| KVK Name | Name of award /awardee | Type of award (Ind./Group/Inst./Farmer) | Awarding Organizations | Amount received |
| --- | --- | --- | --- | --- |
| Raisen | Young Scientist award 2018 | Individual | GKV Society, Agra | - |
| Raisen | Best KVK Extension Scientist award 2018 | Individual | ATDS, Ghaziabad | - |
| Raisen | Young Scientist award | Individual | ASTHA Foundation, Meerut | - |

18. Details of KVK Agro-technological Park .

a) Have you prepared layout plan, where sent?

| S .No. | Name of KVK | Technology park proposal developed(yes/no) | If yes, where sent ? (ZPD/DES/any other, pl. sp.) |
| --- | --- | --- | --- |
| 1 | Raisen | - | - |

b) Details about Technology Park

| Name of KVK | Name of Component of Park | Detail Information (If established) |
| --- | --- | --- |
| Raisen | Crop Cafeteria | - |
| Raisen | Technology Desk | Publication of quarterly news letter. Inventory of technology suitable for the district. Relevant technical folders, literature, leaflet, Pamphlets. Weather forecast & Mandi rate of crop display. Package of practices of important crops. |
| Raisen | Visitors Gallery | Photo gallery – Crops (varieties, disease, IPM technology). Flex board of relevant technology. |
| Raisen | Technology Exhibition | - |
| Raisen | Technology Gate-Valve | - |

c). Crop Cafeteria-

| Sr. No. | Theme of Crop Cafeteria | No. of Crop Cafeteria |
| --- | --- | --- |
| 1 | Kharif season (improved varieties) | 15 varieties of crops |
| 2 | Rabi season (improved varieties) | 20 varieties of crops |

19. Farm Innovators- list of 10 Farm Innovators from the District

| Sr. No. | Name of KVK | Name of Farm Innovator | Name of the Innovation | Address of the farmer with Mobile No. |
| --- | --- | --- | --- | --- |
| 1 | - | - | - | - |

20. KVK interaction with progressive farmers

| Sr. No. | Date and month of interaction programme with progressive farmers | No. of progressive farmers to be participated |
| --- | --- | --- |
| 1 | Kharif Interface Programme (12/9/2018) | 45 |
| 2 | Warehousing Development awareness programme (28/9/2018) | 50 |

21. Outreach of KVK

| Name of KVK | Number of Blocks |  | Number of Villages |  |
| --- | --- | --- | --- | --- |
|  | Intensive | Extensive | Intensive | Extensive |
| Raisen | 4 | 3 | 4 | 100 |

Intensive- OFTS, FLDS etc

Extensive- Literatures, Publications, Awareness programmes etc.

22.  Technology Demonstration under Tribal Sub Plan on Pulses/ Programme on Harnessing Pulses/ Quality Protein Maize, if applicable.

| Sr. No. | Name of crop under Technology demonstration | Area under the programme | No. of Extension Activities | Remarks / Lessons learnt |
| --- | --- | --- | --- | --- |
| 1 | - | - | - | - |

23. KVK Ring

| Sr. No. | Name of Ring Partner | Sharing Activity | Lessons learnt/ Experiences gained. |
| --- | --- | --- | --- |
| 1 | KVK, Bhopal | Improved technology & farm implements. | - |
| 2 | KVK, Sagar | Improved variety of seeds. | - |

24. Important visitors to KVK

| Name of KVK | Name of Visitor | Date of Visit | ICAR | SAUs | Others | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Raisen | Dr. Saumen Saha | 28/7/2018 | ICAR | - | - | - |
| Raisen | Dr. Sanjeev Silawat | 28/7/2018 | - | - | Others | - |
| Raisen | Dr. A.K. Tiwari | 8/1/2019 | - | - | Others | - |
| Raisen | Shri. N.P. Suman | 8/1/2019 | - | - | Others | - |
| Raisen | Dr. Sanjay Vaishampayan | 17/9/2018 | - | SAUs | - | - |
| Raisen | Shri. N.S. Tomar | 24/8/2018 | - | - | Others | - |
| Raisen | Shri. S.S. Chhari | 24/8/2018 | - | - | Others | - |
| Raisen | Shri. Dinesh Kothari | 24/8/2018 | - | - | Others | - |

25. Status of KVK Website:

| Sr. No. | Name of KVK | Date of start of website | No. of updates since inception | No. of visitors |
| --- | --- | --- | --- | --- |
| 1 | Raisen | 29/04/2011 | 155 | 14646 |

26. E-CONNECTIVITY

| Name of KVK | ### Number and Date of Lecture delivered from KVK Hub |  |  |  | ### No. of lectors organized by KVK | ### Brief achievements | ### Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | ### Date | ### No. of Staff attended | ### No. of call received from Hub | ### No. of Call mate to Hub by KVK |  |  |  |
| Raisen | ### - | ### - | ### - | ### - | ### - | ### - | ### - |

27. Status of  RTI

| Sr. No. | Name of KVK | No. of RTI applications received | No. of RTI appeals | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Raisen | - | - | - |

28. Status of Citizen Charter

| Sr. No. | Name of KVK | Query received( Nos) | Query Disposed( Nos) | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Raisen | - | - | - |

29. Attended HRD  Programmes  organized by ZPD

| Name of KVK | Name of Staff | Post held | Programme attended (Nos) | Remarks |
| --- | --- | --- | --- | --- |
| Raisen | Mr. R.S. Raghav | SMS (Soil Science) | 1 | IISS, Bhopal (10 days) |
| Raisen | Dr. Anshuman Gupta | PA (Veterinary Science) | 1 | IISS, Bhopal (10 days) |
| Raisen | Dr. Anshuman Gupta | PA (Veterinary Science) | 1 | ATARI, Jabalpur |
| Raisen | Mr. Pankaj Bhargava | PA (Computer) | 1 | IIITDMJ, Jabalpur (Mobile App Development training) |
|  | Total |  | 4 |  |

| Name of KVK | Total Number of staff Attended HRD Programme organized by ZPD (nos) | Total Number of Programme attended (Nos) |
| --- | --- | --- |
| Raisen | 3 | 4 |

30. Attended HRD Programmes organized by DES

| Name of KVK | Name of Staff | Post held | Programme attended (Nos) | Remarks |
| --- | --- | --- | --- | --- |
| Raisen | Mr. Pradip Kumar Dwivedi | SMS (Plant Protection) | 1 | Beekeeper ASCI Training |
| Raisen | Dr. Mukul Kumar | SMS (Horticulture) | 1 | Mushroom Grower ASCI Training |

| Name of KVK | Total Number of staff Attended HRD Programmes organized by DES (nos) | Total Number of Programmes attended (Nos) |
| --- | --- | --- |
| Raisen | 2 | 2 |

31. Attended HRD  Programmes   by  KVK Staff   (Refresher course, Short course, Training programme etc.)

| Name of KVK | Name of Staff | Post held | Programmes attended (Nos) | Remarks |
| --- | --- | --- | --- | --- |
| Raisen | - | - | - | - |

| Name of KVK | Total Number of staff Attended HRD Programmes by KVK staff (nos) | Total Number of Programmes attended (Nos) |
| --- | --- | --- |
| Raisen | - | - |

32. Agri alert report (Epidemic, high serious  nature problem, Cyclone etc. reported first time to  ZPD, SAU, Agri. Deptt.  and  ICAR)

| Name of KVK | Alert observed | Particulars | Reported to organization |
| --- | --- | --- | --- |
| Raisen | - | - | - |

33. DETAILS OF TECHNOLOGY WEEK CELEBRATIONS

| Name of KVK | Types of Activities | No. of Activities | Number of Participants | Related crop/livestock technology |
| --- | --- | --- | --- | --- |
| Raisen | Gosthies | - | - | - |
| Raisen | Lectures organized | - | - | - |
| Raisen | Exhibition | - | - | - |
| Raisen | Film show | - | - | - |
| Raisen | Fair | - | - | - |
| Raisen | Farm Visit | - | - | - |
| Raisen | Diagnostic Practical's | - | - | - |
| Raisen | Distribution of Literature (No.) | - | - | - |
| Raisen | Distribution of Seed (q) | - | - | - |
| Raisen | Distribution of Planting materials (No.) | - | - | - |
| Raisen | Bio Product distribution (Kg) | - | - | - |
| Raisen | Bio Fertilizers (q) | - | - | - |
| Raisen | Distribution of fingerlings | - | - | - |
| Raisen | Distribution of Livestock specimen (No.) | - | - | - |
| Raisen | Total number of farmers visited the technology week | - | - | - |
| Raisen | Animal health camp | - | - | - |
| Raisen | Awareness programme | - | - | - |
| Raisen | Cashless Transaction Week | - | - | - |
| Raisen | Celebration of important days (Parthenium eradication week, Soil Health Day,International Women Day,National Integrity Day,World environment day,World forestry day,World Water Day) | - | - | - |
| Raisen | Demonstration | - | - | - |
| Raisen | Exposure visit | - | - | - |
| Raisen | Extension activity | - | - | - |
| Raisen | Ex-trainees Meet | - | - | - |
| Raisen | Farmer scientist interaction | - | - | - |
| Raisen | Farmers Training | - | - | - |
| Raisen | Field Day | - | - | - |
| Raisen | Field visit | - | - | - |
| Raisen | Gajarghans Unmulan Pakhwada | - | - | - |
| Raisen | Group Meeting | - | - | - |
| Raisen | Hindi diwas pakhwada | - | - | - |
| Raisen | Jai Kisan Jai Vigyan Sangoshthi | - | - | - |
| Raisen | Narmada sewa Yatra | - | - | - |
| Raisen | News Paper/Mass Media | - | - | - |
| Raisen | Plant health camp | - | - | - |
| Raisen | Plant Protection Week | - | - | - |
| Raisen | Scientists visits in farmers field | - | - | - |
| Raisen | Seed treatment campaign | - | - | - |
| Raisen | Self Help Group convener meet | - | - | - |
| Raisen | Soil health Camp | - | - | - |
| Raisen | Swachha Bharat Abhiyan | - | - | - |
| Raisen | Technology Week | - | - | - |
| Raisen | Van Mahotsava | - | - | - |
| Raisen | Others (Pl. Specify) | - | - | - |

34. INTERVENTIONS ON DROUGHT MITIGATION

Introduction of alternate crops/varieties

| Name of KVK | Crops/cultivars | Area (ha) | Number of beneficiaries |
| --- | --- | --- | --- |
| Raisen | - | - | - |

Major area coverage under alternate crops/varieties

| Name of KVK | Crops | Area (ha) | Number of beneficiaries |
| --- | --- | --- | --- |
| Raisen | - | - | - |

Farmers-scientists interaction on livestock management

| Name of KVK | Livestock components | Number of interactions | No. of participants |
| --- | --- | --- | --- |
| Raisen | - | - | - |

Animal health camps organized

| Name of KVK | Number of camps | No.of animals | No.of farmers |
| --- | --- | --- | --- |
| Raisen | - | - | - |

Seed distribution in drought hit states

| Name of KVK | Crops | Quantity (qtl) | Coverage of area (ha) | Number of farmers |
| --- | --- | --- | --- | --- |
| Raisen | - | - | - | - |

Seedlings and Saplings distributed

| Name of KVK | Crops | Quantity (No.s) | Coverage of area (ha) | Number of farmers |
| --- | --- | --- | --- | --- |
| Seedlings |  |  |  |  |
| Raisen | - | - | - | - |

Bio-control Agents

| Name of KVK | Bio-control Agents | Quantity (q) | Coverage of Area (ha) | No. of farmers |
| --- | --- | --- | --- | --- |
| Raisen | - | - | - | - |

Bio-Fertilizer

| Name of KVK | Bio-Fertilizer | Quantity (kg) | Coverage of Area (ha) | No. of farmers |
| --- | --- | --- | --- | --- |
| Raisen | - | - | - | - |

Verms Produced

| Name of KVK | Verms Produced | Quantity (q) | Coverage of Area (ha) | No. of Farmers |
| --- | --- | --- | --- | --- |
| Raisen | - | - | - | - |

Large scale adoption of resource conservation technologies

| Name of KVK | Crops/cultivars and gist of resource conservation technologies introduced | Area (ha) | Number of farmers |
| --- | --- | --- | --- |
| Raisen | - | - | - |

Awareness campaign

| Name of KVK | Meetings |  | Gosthies |  | Field days |  | Farmers fair |  | Exhibition |  | Film show |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | No. | No. of farmers | No. | No. of farmers | No. | No. of farmers | No. | No. of farmers | No. | No. of farmers | No. | No. of farmers |
| Raisen | - | - | - | - | - | - | - | - | - | - | - | - |

28. Activities performed in Satellite Village on Doubling Farmer’s Income

Information about Satellite Village

| Name of KVK | Block | Village |
| --- | --- | --- |
| Raisen | Sanchi | Bankhedi |

1. Activities for Natural Resource Management:-

| Name of intervention undertaken | Numbers under taken | No of units | Area (ha) | No of farmers covered / benefitted | Remarks |
| --- | --- | --- | --- | --- | --- |
| - | - | - | - | - | - |

2. Activities for Crop Diversification:-

| Name of intervention undertaken | Numbers under taken | No of units | Area (ha) | No of farmers covered / benefitted | Remarks |
| --- | --- | --- | --- | --- | --- |
| Brinjal Seedling | 2000 | 50 | 0.1 | 50 | Hybrid brinjal seedling distribution. |

3. Activities for Crop Production

| Name of intervention undertaken | Area (ha) | No of farmers covered / benefitted | Remarks |
| --- | --- | --- | --- |
| Blackgram | 2.0 | 5 | Variety PU-31 Under CFLD. |
| Soybean | 2.4 | 6 | Variety JS 20-69 Under CFLD. |

4.  Activities for Livestock and Fisheries

| Name of intervention undertaken | Numbers under taken | No of units | Area covered (ha) | No of farmers covered / benefitted | Remarks |
| --- | --- | --- | --- | --- | --- |
| - | - | - | - | - | - |

5. Activities for Livelihood Security to small and marginal land holders:-

| Name of intervention undertaken | Numbers under taken | No of units | Area covered (ha) | No of farmers covered / benefitted | Remarks |
| --- | --- | --- | --- | --- | --- |
| - | - | - | - | - | - |

6.  Activities for Institutional Interventions

| Name of intervention undertaken | No of units | Area covered (ha) | No of farmers covered / benefitted | Remarks |
| --- | --- | --- | --- | --- |
| Assessment of Improved variety of Ginger | 1 | 0.2 | 1 | Improved variety of Ginger (Suprabha). |
| Demonstration of Potassium with STV in Paddy crop. | 2 | 0.4 | 2 | Demonstration of Potassium with STV based nutrition in Paddy crop. |
| Distribution of Drum stick plant | 50 | - | 25 | Variety PKM-1. |

7. Activities for Capacity Building

| Thematic area | No. of Courses | No. of beneficiaries |  |  |
| --- | --- | --- | --- | --- |
|  |  | Male | Female | Total |
| Establishment & management of fruit orchard. | 1 | 27 | - | 27 |
| Capacity building programme for organic farming | 1 | - | 30 | 30 |
| Capacity building programme on organic nutritional gardening. | 1 | - | 20 | 20 |

8. Extension Activities in Satellite Village

| Thematic area | No. of activities | No. of beneficiaries |  |  |
| --- | --- | --- | --- | --- |
|  |  | Male | Female | Total |
| - | - | - | - | - |

29. Activities performed in Nutri-Smart Village

Information about Nutri-Smart Village

| Name of KVK | Block | Village |
| --- | --- | --- |
| Raisen | Sanchi | Bankhedi |

- Innovative practices to promote nutrition-sensitive agriculture and food security :

| Areas | Type of intervention taken (OFT/FLD/Training/ Extension Activity) | Name of intervention taken | Numbers under taken | Quantity (unit) | % change in Nutritional Status | No of beneficiaries |
| --- | --- | --- | --- | --- | --- | --- |
| Diversification and intensification of production | - | - | - | - | - | - |
| Nutrition sensitive livestock and fisheries | Training | Poultry farming | 9 | 15 | 72 | 34 |
| Biodiversity for food & nutrition including forest produces/ Minor Millets | - | - | - | - | - | - |
| Bio-fortification | - | - | - | - | - | - |
| Other (Pl. Specify) | - | - | - | - | - | - |

- Value Chain And Village Trade related Issue:

| Areas | Type of intervention taken (OFT/FLD/Training/ Extension Activity) | Name of intervention taken | Numbers under taken | Quantity | % change in Nutritional Status | No of beneficiaries |
| --- | --- | --- | --- | --- | --- | --- |
| Demand-supply dynamics and market intelligence by the women. | Training | Vegetables marketing | 1 | 250 kg | 12 | 15 |
| Processing and product development of NTFPs by women. | Training | Drumstick processing | 2 | 1 kg | 12 | 10 |
| Food Fortification | Training | Value addition of soybean | 2 | - | 5 | 23 |
| Technology adaptation mechanisms for nutritional security. | FLD/ | Twin wheel hoe | 02 | - | 12 | 15 |
| Economic empowerment through sustainable income generation among women. | Training | Vegetable production | 15 | 100 kg /day | 72 | 30 |
| Other (Pl. Specify) | Training | Mushroom production | 05 | 10 | 16 | 25 |

3. Improving Maternal and Child Nutrition

| Areas | Type of intervention taken (OFT/FLD/Training/ Extension Activity) | Name of intervention taken | Numbers under taken | % change in Nutritional Status | No of beneficiaries |
| --- | --- | --- | --- | --- | --- |
| Strategies and programs for improved maternal nutrition-experiences | - | - | - | - | - |
| Community based strategies to enhance and sustain breast feeding practices and promote early childhood development. | - | - | - | - | - |
| Approaches to improve complementary foods and feeding practices. | - | - | - | - | - |
| Comprehensive approach to address acute malnutrition in children. | - | - | - | - | - |
| Improving nutrition among tribal population with community focus on first 1000 days. | - | - | - | - | - |

4. Nutrition Literacy

| Areas | Type of intervention taken (OFT/FLD/Training/ Extension Activity) | Name of intervention undertaken | Number of Courses | No of beneficiaries |
| --- | --- | --- | --- | --- |
| Nutrition Education and Behaviour | Extension Activity | Awareness programme for nutritional security | 2 | 35 |
| Micronutrient Supplementation | Extension Activity | Poshan mah celebration | 2 | 36 |
| Adolescent and Maternal Nutrition | - | - | - | - |
| Malnutrition Management Service | - | - | - | - |
| Other (Pl. Specify) | Extension Activity | Nutritional security Kisan mobile sandesh | 24 | 3500 women farmer |
|  | Extension Activity | Swachata hi sewa hai | 2 | 56 |

5. Capacity development of women institutions/ SHGs/ FIGs/FPOs

| Area | Name of intervention undertaken | Number of Courses | No of beneficiaries |
| --- | --- | --- | --- |
| Human Resource management for women | - | - | - |
| Capacity development through participatory method | Group formation | 2 | 20 |
|  | Preparation of Vermicompost manure | 02 | 15 |
| Skill development | - | - | - |
| Other (Pl. Specify) | - | - | - |

6. Enabling Suitable governance and policy

| Areas | Name of intervention taken | Numbers under taken | No of Courses | No of beneficiaries |
| --- | --- | --- | --- | --- |
| Role of horticulture and Agriculture Engineering in Nutritional Security | Twin wheel hoe | 5 | 5 | 25 |
| Climate Smart agriculture for Nutritional Security | Nutritional kitchen garden | 4 | 15 | 70 |

7. Institutional Interventions in Collaboration (through KVK, Anganwadi of other Department ) :-

| Name of intervention undertaken | No of collaborative Department | No of beneficiaries | Remark |
| --- | --- | --- | --- |
| Distribution of vegetable seedling | Kvk and women and child development | 10 | - |
| Nutritional literacy | Woman and child development department | 35 | - |
| Seed distribution programme | Woman and child development department | 15 | - |

30. Activities for Sansad Adarsh Gram

Information about Sansad Adarsh Gram

| Name of KVK | Block | Village |
| --- | --- | --- |
| Raisen | - | - |

1. Technologies to be Demonstrated

| Name of Technology | Name of Crop/Enterprise | Area (ha.) | Yield | % change in Yield | No. of farmers benefitted |
| --- | --- | --- | --- | --- | --- |
| - | - | - | - | - | - |

2. Extension Activities

| Name of Activity | Number of Participants/Beneficiaries to be Covered |  |  |  |
| --- | --- | --- | --- | --- |
|  | Farmers | Farm Women | Official | Total |
| - | - | - | - | - |

3. Training Programme

| Name of Activity | Number of Participants/Beneficiaries to be Covered |  |  |  |
| --- | --- | --- | --- | --- |
|  | Farmers | Farm Women | Official | Total |
| - | - | - | - | - |

35. Activities of NICRA (Only NICRA KVKs)

1. Technologies to be Demonstrated

| Name of Technology | Name of Crop | Area (ha.) | Yield | % change in Yield | No. of farmers benefitted |
| --- | --- | --- | --- | --- | --- |
| - | - | - | - | - | - |

2. Extension Activities in NICRA Village

| Name of Activity | Number of Participants/Beneficiaries to be Covered |  |  |  |
| --- | --- | --- | --- | --- |
|  | Farmers | Farm Women | Official | Total |
| - | - | - | - | - |

3. Training Activities in NICRA Village

| Name of Activity | Number of Participants/Beneficiaries to be Covered |  |  |  |
| --- | --- | --- | --- | --- |
|  | Farmers | Farm Women | Official | Total |
| - | - | - | - | - |

4. Activities for Fodder Bank

| Established (Years) | Capacity | Current Status |
| --- | --- | --- |
| - | - | - |

5. Activities for Seed Bank

| Established (Years) | Capacity | Current Status |
| --- | --- | --- |
| - | - | - |

6. Public Representative/District Administration Visited in NICRA Village

| Name of Representative/Officer | Designation | Date of Visit | Any Special Remark by Visitors |
| --- | --- | --- | --- |
| - | - | - | - |

7. Feedback of Farmers for future improvement, if any.

36. Proposed works under NAIP (in NAIP monitoring format) -

37. Case study / Success Story to be developed –

Two best only in the following format

Name of the KVK , TITLE, Introduction, KVK intervention, Output, Outcome, Impact, 2-3 Photographs with caption in .jpeg format.

| Sr. no. | Name of KVK | No. of success stories | No. of case studies |
| --- | --- | --- | --- |
| 1 | Raisen | 2 | - |

Success Story=1

Title:  Higher income through crop diversification.

Introduction:  Mohammad Nazim Ali  is a small farmer of village Mahalpur Patha,  block gairatganj, District- Raisen. He was follow traditional cropping system or cropping pattern based on old parental system like Soybean-Wheat cropping system for round the year.

Intervention: Krishi Vigyan Kendra, Raisen aware to the farmer for crop diversification and new improved variety of Garlic (G-282) through front line demonstration for winter season crop after knowing of this improved variety he was planted of this on one acre of land.

Outcome and Impact: All agronomically practices scientifically followed by farmer with the help of Krishi Vigyan Kendra Raisen. He produce 64 quintal garlic from 1 acre of land and sold out in local market of Raisen with the prices of Rupees 2700/q. He produced good quality garlic which has excellent market attraction. He earned of Rupees 1,72,800 and total expenditure of Crop cultivation was Rs. 59,200. Result as net profit of farmer was Rupees 1,13,600 and BC ratio was 2.91.

Success Story=2

Title: More profit more production through Hi-tech horticulture.

Introduction: Mr. Ankit Gupta S/o Mr. Vinay Gupta is a young & energetic boy belong to Bhopal. He was purchased 6 acre of land in village Gopisur satkunda, block- Sanchi, District- Rasien and started of traditional cultivation of traditional crop but was not getting higher profit.

Intervention: Krishi Vigyan Kendra Raisen was organised of farmers fair and training program for awareness of farmers. Mr Ankit Gupta was awarded about Hi-Tech horticulture light green house and shade net house cultivation through this program. After this Mr Gupta was installed a 1 acre shade net house and planted of tissue culture strawberry plant. KVK, Raisen Scientist was provided of scientifically guidance to strawberry cultivation under shade net house conditions.

Outcome and impact: Strawberry Plant was planted in the month of first week of October and production was started after 60 days. He was produced 80 q/acre of good quality fruit because of shade net house. He was sold out in local market of Raisen as well as Bhopal market on the price of Rupees 75 per kg. He was a round of rupees 6,00,000 and cost of cultivation and installation cost of 1 acre of shade net house was rupees 3,13,000 with the net profit of farmer was Rupees 2,87,000.

38.  Well labeled Photographs in .jpeg format for each activity of the KVK (Soft copies as well as hard copy- specially for all OFT along with the problem) –